STANDARD GUIDELINES FOR

EVALUATION OF BIDS FOR

PROCUREMENT OF WORKS

(First Edition)

MAY, 2002

PAKISTAN ENGINEERING COUNCIL ISLAMABAD

Transparency International Pakistan has incorporated the procedures prescribed in the  PSML  Procurement Manual and is in conformity with the Public Procurement Rules 2004 and National Anticorruption Strategy NACS 2002. Authority means PPRA and Procuring Agency means PSML

September 2004

ACKNOWLEDGMENT

Pakistan  Engineering  Council  extends  deep  appreciations  and  acknowledges  the  tremendous contribution in developing and finalizing this document by the following members of the Standards and Quality Committee:-

1.   Engr. M. Mazhar-ul Islam                                                                                  - Convenor

(Chief Engineer (Contracts), NESPAK, Lahore)

2.   Engr. Prof. Dr. Shafaqat Nawaz                                                                         - Member

(Director, Institute of Chemical Engg. & Tech.,  Punjab University, Lahore)

3.   Engr. Dr. Rafiq-ur-Rehman                                                                                - Member

(Director, Agricultural Mechanization Research Institute (AMRI), Multan)

4.   Engr. Prof. Dr. Bhawani Shankar                                                                       - Member

(Professor & Chairman; Dept. of Electronics & Telecommunication Engineering, Mehran Univ. of Engg. & Tech. , Jamshoro)

5.   Engr. Syed Ali Akbar Shah                                                                                - Member

(Project Director (Housing), Hyderabad Development Authority, Hyderabad)

6.   Engr. Tafsir Ahmad Khan                                                                                  - Member

(Dy. Director (Electrical), Pakistan Standards & Quality

Control Authority (PSQCA), Karachi)

7.   Engr. Naveed-ul-Haq                                                                                        - Member

(Engineer-In-charge, PTV, Quetta)

8.   Engr. Ahtisham-ul-Haq                                                                                      - Member

(Director Development Planning, Central Development Region, Pakistan

Telexom Authority Building, Lahore Cantt.)

9.   Engr. Syed Ehtesham Hussain                                                                            - Member

(Chief Executive, Precision Product Industries, Karachi)

10. Engr. Jilani Yousuf                                                                                             - Member

(Mechanical Engineer, National Refinery Ltd., Karachi)

11. Engr. M. Anwar Qaseem Qureshi                                                                      - Member

(Assistant Director (T), WAPDA, Lahore)

12. Engr. Balal A. Khwaja                                                                                       - Expert

(Ahmad & Ahmad  Engineering ContractsAdvisors/ Corporate Affairs

Consultants, Karachi)

13. Engr. Ijaz Ahmad Khan                                                                                     - Expert

(World Bank Consultant, Lahore, Presently; Partner, National Development Consultants)

14. Engr. Shamshair Dad Khan                                                                                - Expert

(Director, Central Contracts Cell (CCC), WAPDA, Lahore)

PREFACE

Pakistan Engineering Council the Statutory Regulatory body entrusted to regulate the engineering profession  in  Pakistan  has  undertaken  among  others,  the  standardization  of  country  specific documents to regulate and streamline the procurement of engineering consultancy services and procurement of works. Standard Guidelines for Evaluation of Bids for procurement of Works is one such  document  prepared  by  a  team  of  experts  comprising  Employers,  Constructors  and Consultants. It is expected that use of this document will provide an equitable and just basis for evaluation of bids for procurement of works in line with the international practice and relevant PEC Bye-Laws thus minimizing ambiguities  and likely contractual disputes.

Pakistan Engineering Council wishes to place on record its deep appreciation for the tremendous work done by the Standards and Quality Committee and M/s National Development Consultants

(NDC) in finalizing this document. Various engineering organizations and departments are requested to use this document for evaluation of bids for procurement of Works. Any  suggestions to improve this document are welcome which may please be addressed to:

Registrar

Pakistan Engineering Council Ataturk Avenue (East) Sector G-5/2

Islamabad

Tel # 92-51-2276225

Fax # 92-51-2276224

E-mail: registrar @ pec.org.pk

INSTRUCTION TO USERS OF THIS DOCUMENT

The document includes the following:

1.         Background Factors

2.         Essential Steps/Stages of Bid Evaluation

3.         Evaluation Guide

4.         Annexures

5.         Appendices

This document mainly provides the Guidelines for the Executing Agencies/Employer to deal with the Bids received. However the Bidders, before the submission of Bids, can benefit from its contents to know, how their Bids will be treated after submission.

Background  Factors  and  essential  steps/stages  of  Bid  Evaluation  are  explained  to  arrive  at

Evaluation Results to select an Evaluated Responsive Bidder.

Employers    may    add    “Not   Applicable”   in   Annexures   where   they   feel   that   certain information/documents are not related to a particular Tender.

In  the  Appendices,  examples  only  for  Guideline  are  included  from  PEC  Standard  Bidding

Documents of Civil and E&M Works.

This document contains terms Procuring Agency  and Authority which means PSML  and PPRA respectively.

Fraud and Corruption

It is the policy of the PSML  to require its staff and its Vendor / consultants to observe the highest standard of ethics during the selection and execution of such contracts. In pursuance of this policy,  PSML :

(a) Defines, for the purposes of this provision, the terms set forth below:

(i) “Corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, of any thing of value to influence the action of a public official in the selection process or in contract execution; and

(ii)  “Fraudulent practice” means a misrepresentation or omission of facts in order to influence a selection process or the execution of a contract;

(iii) “Collusive practices” means a scheme or arrangement between two or more consultants  with or without the knowledge of PSML , designed to establish prices at artificial, noncompetitive levels and to deprive  PSML  of the benefits of free and open competition;

(iv) “Coercive practices” means harming or threatening to harm, directly or indirectly, persons or their property to influence their participation in a procurement process, or affect the execution of a contract.

(b) will reject a proposal for award if it determines that the consultant recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question;

(c) will sanction a consultant, including declaring the consultant ineligible, either indefinitely or for a stated period of time, to be awarded a PSML  contract if it at any time determines that the consultant has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices.

Amendment-Public Procurement Rules 2004

Rule 13 	Response time.- (1)  	The procuring agency may decide the response time for receipt of bids or proposals (including proposals for pre-qualification) from the date of publication of an advertisement or notice, keeping in view the individual procurement’s complexity, availability and urgency. However, under no circumstances the response time shall be less than fifteen working days for national competitive bidding and thirty working days for international competitive bidding from the date of publication of advertisement or notice. All advertisements or notices shall expressly mention the response time allowed for that particular procurement along with the information for collection of bid documents which shall be issued till a given date, allowing sufficient time to complete and submit the bid by the closing date:

Provided that no time limit shall be applicable in case of emergency.

(2)	The response time shall be calculated from the date of first publication of the advertisement in a newspaper or posting on the web site, as the case may be.

(3)	In situations where publication of such advertisements or notices has occurred in both electronic and print media, the response time shall be calculated from the day of its first publication in the newspapers.

Rule 17.   Qualification of suppliers and contractors.- A procuring agency, at any stage of the procurement proceedings, having credible reasons for or prima facie evidence of any defect in supplier’s or contractor’s capacities, may require the suppliers or contractors to provide information concerning their professional, technical, financial, legal or managerial competence whether already pre-qualified or not:

Provided that such qualification shall only be laid down after recording reasons therefor in writing. They shall form part of the records of that procurement proceeding.

Rule 20.	Principal method of procurement.-  Save as otherwise provided hereinafter, the procuring agencies shall use open competitive bidding as the principal method of procurement for the procurement of goods, services and works.

Rule 21.	Open competitive bidding.- Subject to the provisions of rules 22 to 37 the procuring agencies shall engage in open competitive bidding if the cost of the object to be procured is more than forty thousand rupees.

Rule 28.	Opening of bids.-  (1)  The date for opening of bids and the last date for the submission of bids shall be the same. Bids shall be opened at the time specified in the bidding documents. The bids shall be opened at least thirty minutes after the deadline for submission of bids.

(2)  	All bids shall be opened publicly in the presence of the bidders or their representatives who may choose to be present, at the time and place announced prior to the bidding. The procuring agency shall read aloud the unit price as well as the bid

amount and shall record the minutes of the bid opening. All bidders in attendance shall sign an attendance sheet. All bids submitted after the time prescribed shall be rejected and returned without being opened.

Rule 29. 	Evaluation criteria.- Procuring agencies shall formulate an appropriate evaluation criterion listing all the relevant information against which a bid is to be evaluated. Such evaluation criteria shall form an integral part of the bidding documents. Failure to provide for an unambiguous evaluation criteria in the bidding documents shall amount to mis-procurement.

Rule 30.	Evaluation of bids.-  (1)  All bids shall be evaluated in accordance with the evaluation criteria and other terms and conditions set forth in the prescribed bidding documents. Save as provided for in clause (iv) of sub-rule (3) of rule 36 no evaluation criteria shall be used for evaluation of bids that had not been specified in the bidding documents.

(2)	For the purposes of comparison of bids quoted in different currencies, the price shall be converted into a single currency specified in the bidding documents. The rate of exchange shall be the selling rate, prevailing on the date of opening of bids specified in the bidding documents, as notified by the State Bank of Pakistan on that day.

(3)	A bid once opened in accordance with the prescribed procedure shall be subject to only those rules, regulations and policies that are in force at the time of issue of notice for invitation of bids.

Rule 36.	Procedures of open competitive bidding.-  Save as otherwise provided in these rules the following procedures shall be permissible for open competitive bidding, namely:-

(a)  single stage – one envelope procedure.- Each bid shall comprise one single envelope containing, separately, financial proposal and technical proposal (if any). All bids received shall be opened and evaluated in the manner prescribed in the bidding document.

( b) Technical Proposal single stage – two envelope procedure.- (i)   The bid shall comprise a single package containing two separate envelopes. Each envelope shall contain separately the financial proposal and the technical proposal;

(ii)  	the envelopes shall be marked as “FINANCIAL PROPOSAL” and “TECHNICAL PROPOSAL” in bold and legible letters to avoid confusion;

(iii)  	initially, only the envelope marked “TECHNICAL PROPOSAL” shall be opened;

(iv)  	the envelope marked as “FINANCIAL PROPOSAL” shall be retained in the custody of the procuring agency without being opened;

- the procuring agency shall evaluate the technical proposal in a manner prescribed in advance, without reference to the price and reject any proposal which do not conform to the specified requirements;

(vi)  	during the technical evaluation no amendments in the technical proposal shall be   permitted;

- the financial proposals of bids shall be opened publicly at a time, date and venue announced and communicated to the bidders in advance;

At the time of opening of the Financial Proposals, all members of  Tender / Evaluation Committee  shall sign each and every page of the Proposal, quoted costs, cuttings and overwriting at the time of opening of Technical and Financial proposals as the case may be.

(viii) 	after the evaluation and approval of the technical proposal the procuring agency, shall at a time within the bid validity period, publicly open the financial proposals of the technically accepted bids only. The financial proposal of bids found technically non-responsive shall be returned un-opened to the respective bidders; and

- the bid found to be the lowest evaluated bid shall be accepted.

Rule 2 (h).	“lowest evaluated bid” means,-

(i) a bid most closely conforming to evaluation criteria and other conditions specified in the bidding document; and

(ii)	having lowest evaluated cost;

Note: The Evaluation Committee should first review the financial proposals for arithmetical errors and consistency between the financial and technical proposals (for example, omissions of items included in the technical proposals). Arithmetical errors should be corrected, omitted items evaluated, and the corresponding adjustments made to he offered prices to obtain the final evaluated prices. For example, if a technical proposal indicates the presence of the team leader at the assignment site for 12 months and the financial proposal indicates  only 8 months, and should be calculated by adding the  corresponding amount of staff remuneration to the proposed amount.

Rule 35 Announcement of evaluation reports.-  Procuring agencies shall announce the results of bid evaluation in the form of a report giving justification for acceptance or rejection of bids at least ten days prior to the award of procurement contract.

Note:	The financial proposals of firms lower than 75% shall  be returned unopened,

and after completion of the procedure of evaluation report announcement in

accordance with Rule 35,  the remaining financial proposals should be publicly opened by inviting all the  bidders achieving passing score.

PSML  shall publish in its website the following information: (i) name of all bidders who submitted a bid; (ii) bid prices as read out at bid opening; (iii) name and evaluated prices of all bids that had been evaluated; (iv) name of bidders that were disqualified and the reasons for their disqualification; and (v) name of the bidder recommended for award and reason for recommendation,  duration and summary scope of the contract.

After 10days, evaluation committee shall begin to examine all objections, and evaluation report to be finalized in 6 days ( as the allowable limit for objections is 15 days), signed by all committee members. The ER shall then be approved by the Project Award Committee in 2 days, President - PSML  in 2 Days and letter of Award issued in 2 days. The Contract Agreement must be Signed in 15 days.

Confidentiality.- The procuring agency shall keep all information regarding the bid evaluation confidential until the time of the announcement of the evaluation report in accordance with the requirements of rule 35.

Rule 48.	Redressal of grievances by the procuring agency.- (1) The procuring agency shall constitute a committee comprising of odd number of persons,

with proper powers and authorizations, to address the complaints of bidders that may occur prior to the entry into force of the procurement contract.

(2)	Any bidder feeling aggrieved by any act of the procuring agency after the submission of his bid may lodge a written complaint concerning his grievances not later than fifteen days after the announcement of the bid evaluation report under rule

(3)	The committee shall investigate and decide upon the complaint within fifteen days of the receipt of the complaint.

(4) 	Mere fact of lodging of a complaint shall not warrant suspension of the procurement process.

(5)	Any bidder not satisfied with the decision of the committee of the procuring agency may lodge an appeal in the relevant court of jurisdiction.

Other Two Stage Bidding Procedures.

(c)     	two stage bidding procedure.-

First stage

(i)    	the bidders shall first submit, according to the required specifications, a technical proposal without price;

(ii)	the technical proposal shall be evaluated in accordance with the specified evaluation criteria and may be discussed with the bidders regarding any deficiencies and unsatisfactory technical features;

(iii)	after such discussions, all the bidders shall be permitted to revise their respective technical proposals to meet the requirements of the procuring agency;

(iv)	the procuring agency may revise, delete, modify or add any aspect of the technical requirements or evaluation criteria, or it may add new requirements or criteria not inconsistent with these rules:

Provided that such revisions, deletions, modifications or additions are communicated

to all the bidders equally at the time of invitation to submit final bids, and that

sufficient time is allowed to the bidders to prepare their revised bids:

Provided further that such allowance of time shall not be less than fifteen days in the case of national competitive bidding and thirty days in the case of international competitive bidding;

(v)	those bidders not willing to conform their respective bids to the procuring agency’s technical requirements may be allowed to withdraw from the bidding without forfeiture of their bid security;

Second stage

(vi)	the bidders, whose technical proposals or bids have not been rejected and who are willing to conform their bids to the revised technical requirements of the procuring agency, shall be invited to submit a revised technical proposal along with the financial proposal;

(vii)	the revised technical proposal and the financial proposal shall be opened at a time, date and venue announced and communicated to the bidders in advance; and

(viii)	the revised technical proposal and the financial proposal shall be evaluated in the manner prescribed above. The bid found to be the lowest evaluated bid shall be accepted:

Provided that in setting the date for the submission of the revised technical proposal and financial proposal a procuring agency shall allow sufficient time to the bidders to incorporate the agreed upon changes in the technical proposal and prepare their financial proposals accordingly.

Rule 35 shall apply similar to in case prescribed for single stage – two envelope procedure.

(d)	two stage - two envelope bidding procedure.-

First stage

(i) 	the bid shall comprise a single package containing two separate envelopes. Each envelope shall contain separately the financial proposal and the technical proposal;

(ii)	the envelopes shall be marked as “FINANCIAL PROPOSAL” and “TECHNICAL PROPOSAL” in bold and legible letters to avoid confusion;

(iii)	initially, only the envelope marked “TECHNICAL PROPOSAL” shall be opened;

(iv) 	the envelope marked as “FINANCIAL PROPOSAL” shall be retained in the custody of the procuring agency without being opened;

(v)	the technical proposal shall be discussed with the bidders with reference to the procuring agency’s technical requirements;

(vi)	those bidders willing to meet the requirements of the procuring agency shall be allowed to revise their technical proposals following these discussions;

(vii) 	bidders not willing to conform their technical proposal to the revised requirements of the procuring agency shall be allowed to withdraw their respective bids without forfeiture of their bid security;

Second stage

(viii) 	after agreement between the procuring agency and the bidders on the technical requirements, bidders who are willing to conform to the revised technical specifications and whose bids have not already been rejected shall submit a revised technical proposal and supplementary financial proposal, according to the technical requirement;

(ix) 	the revised technical proposal along with the original financial proposal and supplementary financial proposal shall be opened at a date, time and venue announced in advance by the procuring agency:

Provided that in setting the date for the submission of the revised technical proposal and supplementary price proposal a procuring agency shall allow sufficient time to the bidders to incorporate the agreed upon changes in the technical proposal and to prepare the required supplementary financial proposal; and

(x) 	the procuring agency shall evaluate the whole proposal in accordance with the evaluation criteria and the bid found to be the lowest evaluated bid shall be accepted.

Rule 35 shall apply similar to in case prescribed for single stage – two envelope procedure.

Rule 37.	Conditions for use of single stage two envelope, two stage and two stage two envelope bidding procedures.- Single stage one envelope bidding procedure shall ordinarily be the main open competitive bidding procedure used for most of the procurement. Other appropriate procedures of open competitive bidding shall be selected in the following circumstances, namely:-

(a)  	single stage two envelope bidding procedure shall be used where the bids are to be evaluated on technical and financial grounds and price is taken into account after technical evaluation;

(b) 	two stage bidding procedure shall be adopted in large and complex contracts where technically unequal proposals are likely to be encountered or where the procuring agency is aware of its options in the market but, for a given set of performance requirements, there are two or more equally acceptable technical solutions available to the procuring agency; and

(c) 	two stage two envelope bidding method shall be used for procurement where alternative technical proposals are possible, such as certain type of machinery or equipment or manufacturing plant.

The  Document shall also specify the mandatory Non Responsive Conditions for the information of Bidders.

Major deviations to the commercial requirements and technical specifications are a basis for the rejection of bids. As a general rule, major deviations are those that, if accepted, would not fulfill the purposes for which the bid is requested, or would prevent a fair comparison with bids that are properly compliant with the bidding documents. Examples of major deviations include:

- Stipulating price adjustment when fixed price bids were called for

- Failing to respond to specifications by offering instead a different design or product that does not offer substantial equivalence in critical performance parameters or in other requirements

- Phasing of contract start-up, delivery, installation, or construction not conforming to required critical dates or progress markers

- Subcontracting in a substantially different amount or manner than that permitted

- Refusing to bear important responsibilities and liabilities allocated in the bidding documents, such as performance guarantees and insurance coverage

- Taking exceptions to critical provisions such as applicable law, taxes and duties, and dispute resolution procedures

- Those deviations that are specified in the ITB as requiring rejection of the bid (such as, in the case of works, participating in the submission of another’s bid other than as a subcontractor).

- Refusing  to Sign Integrity Pact.

Rule 33.	Rejection of bids.-  (1)  The procuring agency may reject all bids or proposals at any time prior to the acceptance of a bid or proposal. The procuring agency shall upon request communicate to any supplier or contractor who submitted a bid or proposal, the grounds for its rejection of all bids or proposals, but is not required to justify those grounds.

(2) 	The procuring agency shall incur no liability, solely by virtue of its invoking sub-rule (1)  towards suppliers or contractors who have submitted bids or proposals.

(3) 	Notice of the rejection of all bids or proposals shall be given promptly to all suppliers or contractors that submitted bids or proposals.

Rule 34.	Re-bidding.-  (1) If the procuring agency has rejected all bids under rule 33 it may call for a re-bidding.

- The procuring agency before invitation for re-bidding shall assess the reasons for rejection and may revise specifications, evaluation criteria or any other condition for bidders as it may deem necessary.

TABLE OF CONTENTS

DESCRIPTION                                                                              PAGE NO.

1.0                   BACKGROUND FACTORS ........................................................................... 1

1.1       Instructions to Bidders.............................................................................. 1

1.2       Elements of Bid Evaluation ....................................................................... 1

2.0                   ESSENTIAL STEPS/STAGES OF BID EVALUATION ............................... 2

2.1       Bid Opening............................................................................................. 2

2.2       Stages of Bid Evaluation........................................................................... 2

3.0                   EVALUATION GUIDE.................................................................................... 3

3.1       Bid Opening Record ................................................................................ 3

3.2       Bid Validity.............................................................................................. 4

3.3       Principles of Evaluation............................................................................. 4

3.4       Preliminary Examination of Bids................................................................ 4

a)         Verification .................................................................................. 5 b)         Eligibility ...................................................................................... 5 c)         Bid Security................................................................................. 5 d)         Completeness of Bid .................................................................... 5 e)         Substantial Responsiveness........................................................... 6 f)          A bid is likely not to be considered in the light of paras(a)

to (e) above if; ............................................................................. 6

g)         Results of Preliminary Examination................................................ 7

3.5       Detailed Examination of Bids .................................................................... 7

a)         Correction for Errors.................................................................... 7 b)         Correction for Provisional Sums ................................................... 8 c)         Modifications and Discounts......................................................... 8 d)         Additions ..................................................................................... 8 e)         Adjustments................................................................................. 8 f)          Minor Deviations.......................................................................... 8

3.6       Determination of Award ........................................................................... 9

a)         Cross-Discounts .......................................................................... 9 b)         Qualification............................................................................... 10 c)         Proposed Award ....................................................................... 10 d)         Award of Contract..................................................................... 10

3.7       Evaluation Guidance............................................................................... 10

ANNEXURES

Annex-I           Bid Opening Checklist............................................................................ 11

Annex-II          Bid Evaluation Tables............................................................................. 12

Table 1: Identification............................................................................. 12

Table 2: Bidding Process........................................................................ 13

Table 3: Bid Submission and Opening..................................................... 14

Table 4: Summary of Bid Prices (As Read Out) ...................................... 15

Table 5: Result of Preliminary Examination.............................................. 16

Table 6: Corrections and Unconditional Discounts................................... 17

Table 7: Additions, Adjustments and Priced Deviations ........................... 18

Table 8: Proposed Contract Award........................................................ 19

Annex-III         Example of Preliminary Examination........................................................ 20

Annex-IV         Bid Evaluation Checklist......................................................................... 21

APPENDICES

Appendix-A (Evaluation Criteria Example For Civil Works)................................ 22

Appendix-B (Evaluation Criteria Example For E&M Works).............................. 23

Annexure ( Integrity Pact )…………………………………………………..

1.0     BACKGROUND FACTORS

1.1       Instructions to Bidders

1.1.1       The eligible bidders who are interested to participate in the bidding process are issued the bidding documents for the specific contract for procurement of Works. The most relevant section of Bidding Documents for the bidders at bidding stage is the Instruction to Bidders (ITB). The clarity, conciseness and completeness of the Section i.e. ITB is most important because the bidders are required to seek guidance from the Employer and abide by these instructions for finalization of a real, meaningful, rational and complete bid conforming to the requirements of the Bidding Documents.

The ITB are required to cover all aspects for finalization of bid by following very clearly laying down the limitations for the bidders which must be observed and clearly  laying  down  the  consequential  penalties  in  case  these  limitations  are violated  in  preparation  of  the  bid.  The  efficiency  in  completion  of  project implementation by quick decision making, procurement at most economical/least cost to the Employer by determination of the lowest evaluated bid and finally the completion of this part of the procurement process in a transparent manner are the cornerstones of a credit-worthy bid-evaluation process.

1.2       Eleme nts of Bid Evaluation

1.2.1       The most important elements that figure in the bid evaluation process are essential part of the ITB. These elements have to be considered and accorded appropriate weightage to determine the LOWEST EVALUATED RESPONSIVE BIDDER

(LERB) for award of contract. These elements generally include:-

i)                Deadline  for  submission  (date,  time  and  place),  handling  of  bids received after deadline.

ii)               Eligibility of Bidders in the light of the PEC Bye-Laws, i.e, holding a current valid licence to practice as constructor.

iii)              Qualification of the Bidder i.e,

-        Review   of   updated   information   on   the   sub-elements   for prequalification to establish continued status as at the time of pre-qualification, or

-        Assessment of qualification of the Bidder from data provided for post-qualification.

iv)              Completeness of bid i.e, provision of all the essential information in response to bidding documents/any Addendum, if issued.

v)               Clear    information    about    Foreign    Exchange    Currency(FEC)

requirements, if needed.

vi)              Validity of the bid viz-a-viz the requirements of the bid documents in terms of time.

vii)             Provision of Bid Security requirements in the specified format from an acceptable source and in the requisite amount fixed in the ITB/Bid Data Sheet.

viii)             The acceptability of bid in terms of its validity due to its signing by the duly authorized representative and inclusion of Letter of Authority.

ix)              Conformance of bid to technical and commercial requirements of the bid documents.

x)               Precise, clear and unambiguous provisions for handling variations from the above requirements.

2.0      ESSENTIAL STEPS / STAGES OF EVALUATION

2.1       Bid Opening

2.1.1       One of the most important activity in procurement is the bid opening in the presence  of  the  representatives  of  bidders  (who  choose  to  attend)  at  the designated place, on the fixed date and time. This is a vital step towards making the process transparent. The bid opening committee has to publicly announce, the following most important information about each bid and sign the tabulated sheet simultaneously:-

(i)      Name of bidder, single or a JV of firms.

(ii)     The bid price

(iii)    Discounts (unconditional/conditional), if any.

(iv)    Modifications to the Bid, if any

(v)     Withdrawal of bids(s), if any

(vi)    Presence/absence of bid security and its amount.

(vii)   Similar information on alternate bids, if any.

2.1.2       The representatives of the bidders are also required to sign their presence and also  desirably  accept  the  announced  information  about  their  bids.  All  the information pertaining to this activity has to be retained as part of the important procurement record for the Auditor General’s/Funding Agency (if foreign source) reference. The committee is also required to prepare formal minutes of the bid opening and put it up for information of  the persons/offices responsible for overall project implementation.

2.2       Stages of Bid Evaluation

2.2.1       Prior  to  proceeding  with  the  laying  down  of  guidelines/instructions  for  the evaluation  of  bids  the  three  important  stages  of  bid  evaluation  are  listed  as follows:-

i)       Preliminary Examination to include:-

(a)     Does the bidder hold a valid licence from the PEC and fall within the category

allowed to participate for the size of the project?

(b)    Has  the  bid  been  properly  signed  by  the  authorized  person(s)  and  the authorization is available/bonafide?

(c)     Is the bid accompanied by the required securities i.e. the amount is adequate as required in ITB/Bid data Sheet, conforms to the specified format and issued by an acceptable source?

(d)    Does  the  bid  generally  and  substantially  meets the requirements of the bid documents?

(e)     Does  the  bid  have  adequate  provision  for  clarifications,  if  required  for substantiation of any elements desired by the Employer?

(f)       Check for arithmetic errors and acceptance of corrections by the bidders.

(g)     Agreed to Sign Integrity Pact

ii)     Evaluation/Comparison of bids

(A)    Determination  of  the  evaluated  bid  price  for  each  bid  by  making  any adjustments, as required which may include:-

(a)     Application of unconditional discounts/conditional discounts.

(b)    Making correction of errors.

(c)    Excluding Provisional Sums & Contingencies.

(d)    Determination/making adjustments for minor (acceptable) deviations on technical/commercial grounds.

(e)    Making  adjustments  for  varying  times  for  completion  offered  by  the bidders, if acceptable.

(B)    Consideration of the effect of any loading of bid.

3.0       EVALUATION GUIDE

3.1       Bid Opening Record

3.1.1       All bidders or their representatives are invited to attend the bid opening, where data about bids are read-out and recorded, along with a list of attendees. The record  is  prepared  for  prompt  transmittal  to  the  overall  incharge  of  project implementation. Bid opening procedures are described in the ITB. To assist in carrying out the opening and preparing of the record, a checklist is provided as Annex-I to this document. The checklist should preferably be filled-out for each bid  during  the  actual  reading  out  at  the  bid-opening.  The  reading  and announcement should be from the original version of each bid, and the actual amounts and other key details read out should be circled for later verification. If bids are expressed in a single currency, other currency needs expressed as a percentage should also be recorded.

3.1.2       Any envelopes containing substitutions, modifications, or withdrawals must be subject to the same level of scrutiny, including the reading out of critical details. Failure to read out such information and include it in the written record may result in denial of its inclusion in bid evaluation. If a bid has been withdrawn by telex, fax

or E-mail, it should nonetheless be read out informing its status of withdrawal to all the participants of the Bid opening and should not be returned to the bidder until the authenticity of the withdrawal notice has been confirmed.

3.1.3       As stated in the ITBs, no bids should be rejected at the bid opening except those received  after  the  deadline  for  receipt  of  bids.  Such  bids  shall  be  returned unopened to the bidder. A summary of the read-out bid prices should be provided in Table-4 of Annex-II of this document.

3.2       Bid Validity

3.2.1       The duration of the validity of each bid should be the one specified in the ITB and should be confirmed in the signed Form of Bid. If exceptional circumstances occur in which award cannot be made within the validity period, extensions in writing should be requested from the bidders, in accordance with the ITB. Extensions to the validity of bid security should also be requested from the bidders, if necessary. Particular care must be taken in cases where the deadline for submission (or for opening) of bids can be extended, as the duration of bid security is frequently provided in terms of an expiration date of bid validity. In contrast, bid validity is specified in terms of an interval after the deadline for receipt or the date of bid opening. Any extensions are to be listed in the form as given at Table  -3 of Annex-II of this document.

3.3       Principles of Evaluation

3.3.1       After  the  public  opening  of  bids,  information  relating  to  the  examination, clarifications, and evaluation of bids shall not be disclosed to bidders or  other persons not officially concerned with this process until the successful bidder is notified of the award of contract. Appointment by the executing agency of an evaluation  committee,  consisting  of  a  minimum  of  three  qualified  members  is recommended who should work in a secure office where all bidding documents can be kept. There may be a considerable advantage if the  members who participated in the preparation of the bidding documents are included in the bid evaluation committee. It is also recommended to prevent the un-realistic time gap between submission of Bids and Evaluation process completed because such gaps may create opportunities for disclosure of contents of Bids/informations.

3.3.2       If  warranted,  occasionally,  the  executing  agency  may  request  clarifications  of bidders concerning ambiguities or inconsistencies in the bid. As required in the ITB, such requests shall be in writing, and no change in the price or scope of the originally offered works shall be sought or accepted, except for the correction of the arithmetic error and to understand the bidders intentions for a decision on its responsiveness.  The  responses  from  bidders  shall  also  be  in  writing.  No circumstances shall justify meeting or conversations between the executing agency, its evaluation committee (or its consultants) and bidders during the bid evaluation process.

3.4       Preliminary Examination of Bids

The  evaluation  process  should  begin  immediately  after  bid  opening.  The  purpose  of preliminary  examination  is  to  identify  and  reject  bids  that  are  incomplete,  invalid,  or substantially  non-responsive  to  the  bidding  documents  and  therefore  are  not  to  be considered further. The following checks should be applied:

(a)          Verification: Attention should be directed towards deficiencies that, if accepted, would provide unfair advantage to the bidder. Sound judgment must be used: for example,  simple  omissions  or  mistakes  arguably  occasioned  by  human  error should not be considered an adequate ground for rejection of the bid. Rarely is a bid perfect in all respects. However, the validity of the bid itself, for example, its signatures, must be valid, bonafide and affixed by the authorized representative.  If the bidder is a joint venture, the joint venture agreement must be submitted; all copies of the bid, as the first step should be compared with the original and corrected accordingly, if necessary. Thereafter, the original should be kept in a safe location, and only copies should be used in evaluation. In case error/omission in

Copies, Original should govern.

(b)          Eligibility: Besides any other requirements of the Employer, the bidder must be a PEC licenced constructor. All partners to a joint venture shall also be similarly registered, i.e. local or foreign and the joint venture shall be registered in Pakistan with PEC. If prequalification has taken place, only bids from prequalified bidders can be considered and the juridic entities of the prequalified bidders may not be modified in the submission of bids. The bidder (including all members of  a joint venture and subcontractors) may be disqualified if affiliated with a firm that has provided related consulting services, as per PEC Bye-Laws.

(c)           Bid Security: The bidding document may require submission of a bid security. If so, the bid security must conform to the requirements of the ITB, and it must accompany the bid. If the bid security is issued as a bank guarantee, it must be consistent with the wording of the bid security form provided in the bidding document. Submission of a copy of the security is unacceptable. Furthermore, securities for an amount smaller or for a period shorter than the one specified in the ITB are not acceptable. However if Bid Security amount is short within 10% of Bid Security amount and period is short by one or two days, Employer should consider the same as minor deviation provided the bidder(s) undertake to make them up in response to the queries. The security for a bid submitted by a joint venture should be in the name of the joint venture.

(d)          Completeness of  Bid:  Unless the bidding documents have specifically allowed, bids not offering all of the required items should ordinarily be considered non- responsive. However, under works contracts, missing prices for occasional work items are considered to be included in prices for closely related items elsewhere; if such  provision  exists  in  the  preamble  of  Bill  of  Quantity.  If  any  erasures, interlineation,  additions,  or  other  changes  have  been  made,  these  should  be initialed by the bidder. Exception from bid conditions are acceptable if they are corrective, editorial, explanatory; otherwise, they should be treated as deviations and should be analyzed as per para 3.4 (e) hereinafter. Missing pages in the

original copy of the bid which affect the ranking of the Bidders may be a cause for rejection of the bid.

(a)          Correction for Errors: The methodology for correction of computational errors is described in the ITB. The read-out bid prices and their corrections should be noted in Table-6 column-d of Annex-II. The corrections are considered binding on the bidder. Unusual or large corrections that could affect the comparative ranking of bids should be explained in footnotes.

“The tender shall contain no alterations, omissions or additions, except to comply with instructions issued by the Employer, or as are necessary to correct errors made by the bidder, in which case such corrections shall be initialed by the person or persons signing the tender”.

“The Correction shall be made by striking a line over the wrong amount, and writing the correct amount separately. The use of White Fluid for correction of error is not allowed. The Correction shall be made by striking a line over the wrong amount, and writing the correct amount separately”

(b)          Correction for Provisional Sums :  Bids may contain provisional sums set by the Employer/Engineer for contingencies or for nominated subcontractors, etc. As these sums are the same for all bids, they should be subtracted from the read out prices in Table 6, column-e of Annex-II to allow for a proper comparison of bids in subsequent steps. However, those provisional sums set aside for Day-work etc, where priced competitively, should not be included in the deductions.

(e)           Substantial Responsiveness:

(A) Major (Material) deviations

Major deviations to the commercial requirements and technical specifications are a basis for the rejection of bids. As a general rule, major deviations are those, that if accepted, would not fulfill the purposes for which the bid is requested, or would prevent a fair comparison or affect the ranking of the  bids that are compliant with the bidding documents. Examples of major deviations include:-

(i)        Stipulating price adjustment when fixed price bids were called for.

(ii)        Failing to respond to specifications.

(iii)       Failing  to  comply  with  Mile-stones/critical  dates  provided  in  Bidding

Documents.

(iv)       Subcontracting contrary to the Conditions of Contract specified in Bidding

Documents.

(v)      Refusing to bear important responsibilities and liabilities allocated in the Bidding  Documents,  such  as  performance  guarantees  and  insurance coverage.

(vi)       Taking exception to critical provisions such as applicable law, taxes and duties and dispute resolution procedures.

(vii)      Those deviations that are specified in the ITB requiring rejection of the bid

(such as, in the case of works, participating in the submission of other bids other than as a subcontractor).

(viii)	   Refuses to sign Integrity Pact.

(B) Minor Deviations

Bids that offer deviations acceptable to the Employer and which can be assigned a monetary value may be considered substantially responsive at least as to the issue of fairness. This value would however be added as an adjustment for evaluation purposes only  during the detailed evaluation process

(f)            A bid is not to be considered in the light of paras(a) to(e) above  if;

(i)        It is submitted by a Bidder who has participated in more than one Bid.

(ii)        It is received after the time and date fixed for its receipt.

(iii)       It is submitted through fax, telex, telegram or e-mail.

(iv)       It is not accompanied with Bid Security.

(v)        It is unsigned.

(vi)       Its validity is less than specified.

(vii)      It is submitted for incomplete Scope of Work.

(viii)     It indicates completion date later than specified.

(ix)       It indicates that prices quoted are not firm during currency of the contract except those prices where escalation/adjustments are permitted in the Conditions of Contracts.

(x)        It  indicates  that  material  to  be  supplied  does  not  meet  the  eligibility requirements.

(xi)       It indicates that Bid Prices do not include the amount of taxes & duties.

(xii)      If Bidder refuses to accept the arithmetic corrections.

(xiii)     It      is      materially      and      substantially      different      from      the

Conditions/Specifications of Bidding Documents.

(xiv)     It provides Sub-contracting, contrary to conditions specified in the Bidding

Documents.

(xv)      It   fails   to   comply   Mile-Stones/critical   dates   specified   in   Bidding

Documents.

- The bidder is not valid license holder of the PEC.

- Fails to Sign Integrity .

(g)           Results of Preliminary Examination

The results of preliminary examination should be presented in Table-5 of Annex- II.  It  should  be  however  realized  that  Table  1  to  Table  4  Annex-II are for summarizing the essential information from the bids. If the bid fails in preliminary acceptance,  the  reasons  must  be  clearly  explained  in  footnotes  or  in  an attachment, as necessary. An example is shown in Annex-III. Executing agencies may find it useful to include additional tables for itemization of responsiveness to a list of technical or commercial specifications. These should be attached to Table-5

of Annex-II.

3.5       Detailed Examination of Bids

3.5.1       Only Responsive  bids as a result of preliminary examination shall be examined in detail.

(c)           Modifications and Discounts: In accordance with the ITB, bidders are allowed to submit, prior to bid opening, modifications to their original bid. The impact of modifications should be fully reflected in the examination and evaluation of the bids. These modifications may include either increases or discounts to the bid amounts that reflect last-minute business decisions. Accordingly, the original bid prices should be modified at this point in the evaluation. Discounts offered in accordance with the ITB that are conditional on the simultaneous award to the same bidder of other contracts (cross-discounts) shall not be incorporated until the  completion  of  evaluation  of  other  contracts.  The  effect  of  unconditional discounts (or alternatively, increases) should be shown as in Table-6 of Annex-II

(columns g and h). Any discount expressed in percent must be applied to the appropriate  base  specified  in  the  bid  (i.e.,  check  to  see  if  it  applies  to  any provisional sums). Employer may reserve the right to consider the cross discounts.

(d)          Additions:  Omissions to the bid should be compensated for by adding the estimated costs for remedying the deficiency. Where items missing in some bids are present in others, average of the quoted prices could be used to compare competitors’ bids. The cost determined should be expressed in the evaluation currency and shown in Table-7, column c of Annex-II.

(e)           Adjustments: The ITB specifies which of the factors will be taken into account for adjustments of bid price in the bid evaluation. The methodology used in evaluation of these factors should be precisely described in the bid evaluation report  and  should  be  fully  consistent  with  the  ITB  provisions.  Bonuses  or additional credits that reduce the evaluated bid price will not be considered in the bid evaluation for features that exceed the requirements stated in the bidding

documents, unless specifically provided for in the ITB. The value of adjustments will be expressed in terms of cost, for all works contracts, and should be shown in Table-7 column-d of Annex-II.

(f)       Minor Deviations: As discussed under para 3.4 (e), bids with minor deviations may be considered substantially responsive if their further consideration assigns a monetary cost or adjustment to the bid for the purpose of bid comparison:-

(i)        Requests for deviations that are expressed by the bidder in vague terms, such as “we would like an increase in the amount of mobilization advance” or  “we  wish  to  discuss  changes  in  the  completion  schedule”  should ordinarily be ignored in bid evaluation (if the same is withdrawn by the bidder upon subsequent  clarifications) provided that the same do not affect the relevant ranking of the bidder, but shall be considered deviation if  adjustment  procedure  for  late  completion  or  such  other  items  are mentioned  in  Evaluation  Criteria.  Also  a  categorical  statement  by  the bidders taking exception to a requirement in the bidding documents should be treated as a deviation.

(ii)        If a bid requires a faster payment than specified in the bidding documents, then adjustment should be based on the prospective benefit to the bidder. This situation assumes use of a discounted cash flow using the prevailing commercial interest rates for the currencies of the bid, or ITB foresees the eventuality and specifies a rate.

(iii)       If a bid provides for a completion that is beyond the date specified in the bidding documents but that is nonetheless technically acceptable to the executing agency, the time advantage given should be assessed and a penalty specified in the light of the  ITB or, if one is not provided, it should be  based  on  the  rate  of  liquidated  damages  specified  in  the  bidding documents.

3.5.2       Methods of detailed Evaluation for Civil Works and E&M Works, Contracts are attached at Appendix-A & B for Guidance.

3.6       Determination of Award

3.6.1.      Before arriving at a decision of award Table 7 of Annex-II be completed for the lowest evaluated Bidder.

(a)       Cross-Discounts: Where there are conditional discount offered in the event that more than one contract will be awarded to the same bidder, Bid evaluation in such cases can be quite complicated. The sizes of cross discounts offered by each bidder may vary with the potential number of contracts awarded. The ITB may also limit the number of total value of awards to a bidder on the basis of its financial and technical capacity. Thus, a bidder offering the lowest evaluated bid on a particular contract

may be denied award because of such a restriction. The executing agency at its discreation may select the optimum combination of awards (in case of slice and package bidding) on the basis of least overall cost of the total contract package, consistent with the qualification criteria, subject to the provision of such possibility in the Tender Documents, presentations of the calculations should be made on an attachment to the report, which should include the bid evaluation(s) for the other contracts, if they have been evaluated separately.

(b)       Qualification: If prequalification was conducted, the bidder whose bid is the  lowest  evaluated  should  receive  the  award,  unless  the  bidder’s qualifications have since materially deteriorated or the bidder has since received additional work that over-stresses its capacity. The executing agency should satisfy itself fully on both accounts. The rejection of a bid for reasons of qualification requires substantial justification, which should be clearly documented in attachments to the report.

(c)       Proposed Award: The amount of the proposed award shall be the bid price as submitted by the bidder and adjusted as described in the ITB for corrections and any discounts (including cross-discounts). Adjustments to the  final  price  and  scope  of  the  contract  to  correct  for  acceptable omissions in the bid may be negotiated with the lowest evaluated bidder. Table-8 Annex-II should be filled out to establish the actual amount of the

contract award.

If (i) none of the bids are found to be responsive, (ii) bids are un- reasonably  high  in  price  compared  with  earlier  estimates, or

(iii) none of the bidders are qualified, the Employer may consider rejection of all bids.

(d)       Award  of  Contract: Bid securities of unsuccessful bidders should be returned promptly after award has been made and contract signed with the selected bidder after satisfactory submission of a performance security and fulfillment of other conditions. The executing agency may consider seeking an appropriate extension of time for the bid validity and the accompanying bid security of the next two or more (if the executing agency feels it to be beneficial) lowest evaluated responsive bidders, if the award expected to be delayed beyond the validity dates of the bids and bid security.

3.7       Evaluation Guidance

Annex-II & Annex IV are particularly added for guidance of the Employer whereas Annex-III is an example of Preliminary Examination and Annex- IV is the Bid Evaluation Check List.

BID OPENING CHECKLIST

(To be filled-out for each bid as it is read-out)

Annex-I

Contract Reference: ___________________________________________________________ Bid Opening Date: ______________________________ Time: ________________________ Name of Bidder: _____________________________________________________________

(a)        Is outer envelope of bid sealed?

(b)       Is Form of Bid completed and signed?

(c)        Expiration date of bid :              ________________________

(d)       Is documentary authority for signing enclosed?

(e)        Amount of bid security (as required):     _______________________

(f)        Describe any “Substitution,” “Withdrawal,” or “Modification” submitted.

(g)        Describe any alternative bid made.

(h)        Describe any discounts or modifications offered.

(i)         Additional comments

(j)        Name of bidder or his representative who attended bid opening.

(k)       Total bid price: _________________________________________________________

(If bid is for a package of contracts, the price for each slice should be read out). Signed by:

____________________ Members of Committee

___________________ Bidders Representatives

_____________________

Convenor of Committee

Annex-IV

BID EVALUATION CHECKLIST

1.         Explain any inconsistencies between prices and modifications to prices read-out at bid opening (and written into the record) and presented in Table-4 of Annex-II.

2.         Provide details on eliminating any bids during preliminary examination (Table-5). Copy selected pages from bids, as desirable, to show examples of objectionable features.

3.         If  provisional  sums  in  Table-6  vary  among  bidders,  explain.  Explain  any  substantial corrections for computational errors that may have any effect on the ranking of bidders.

4.         The additions, adjustments, and priced deviations in Table-7 require detailed explanations where they may cause an effect upon the ranking of bidders.

5.         Explain any cross-discount [para 3.6.1(a)] not read out and recorded at bid opening. In addition, attach copies of any evaluation reports for the other related contracts awarded to the same bidder in case of slice and package contracts.

6.         Provide detailed reasons for refusing to award a contract to a party other than the lowest evaluated bidder.

7.         An attachment to Table-8 should explain adjustments to the price provided on the Item-8. Explain any loading to incomplete scope of bid and contract conditions.

8.         Maintain in the record, copies of any correspondence from bidders that raise objections to the bidding and evaluation process, together with detailed responses.

9.         Attach copies of any letter to bidders requesting clarifications. Provide copies of responses.

10.       Bid evaluation report to contain as Attachment.

- Ensure that the bid evaluation report is double-checked, paginated, and complete.

Amendment-Public Procurement Rules 2004

Rule 29.   Evaluation criteria.- Procuring agencies shall formulate an appropriate evaluation criterion listing all the relevant information against which a bid is to be evaluated. Such evaluation criteria shall form an integral part of the bidding documents. Failure to provide for an unambiguous evaluation criteria in the bidding documents shall amount to mis-procurement.

Rule 30.         Evaluation of bids.-  (1)  All bids shall be evaluated in accordance with the evaluation criteria and other terms and conditions set forth in the prescribed bidding documents. Save as provided for in clause (iv) of sub-rule (3) of rule 36 no evaluation criteria shall be used for evaluation of bids that had not been specified in the bidding documents.

Rule 35 Announcement of evaluation reports.-  Procuring agencies shall announce the results of bid evaluation in the form of a report giving justification for acceptance or rejection of bids at least ten days prior to the award of procurement contract.

PSML  shall publish in its website the following information: (i) name of all bidders who submitted a bid; (ii) bid prices as read out at bid opening; (iii) name and evaluated prices of all bids that had been evaluated; (iv) name of bidders that were disqualified and the reasons for their disqualification; and (v) name of the bidder recommended for award and reason for recommendation,  duration and summary scope of the contract.

After 10days, evaluation committee shall begin to examine all objections, and evaluation report to be finalized in 6 days ( as the allowable limit for objections is 15 days), signed by all committee members. The ER shall then be approved by the Project Award Committee in 2 days, President - PSML  in 2 Days and letter of Award issued in 2 days. The Contract Agreement must be Signed in 15 days.

Confidentiality.- The procuring agency shall keep all information regarding the bid evaluation confidential until the time of the announcement of the evaluation report in accordance with the requirements of rule 35.

Rule 48.	Redressal of grievances by the procuring agency.- (1) The procuring agency shall constitute a committee comprising of odd number of persons, with proper powers and authorizations, to address the complaints of bidders that may occur prior to the entry into force of the procurement contract.

(2)	Any bidder feeling aggrieved by any act of the procuring agency after the submission of his bid may lodge a written complaint concerning his grievances not later than fifteen days after the announcement of the bid evaluation report under rule 35.

(3)	The committee shall investigate and decide upon the complaint within fifteen days of the receipt of the complaint.

(4) 	Mere fact of lodging of a complaint shall not warrant suspension of the procurement process.

(5)	Any bidder not satisfied with the decision of the committee of the procuring agency may lodge an appeal in the relevant court of jurisdiction.

EVALUATION CRITERIA EXAMPLE FOR CIVIL WORKS

Evaluation and Comparison of Bids

APPENDIX-A

1.         The Employer will evaluate and compare only the bids determined to be substantially responsive.

2.         In evaluating the bids, the Employer will determine for each bid the evaluated bid price by adjusting the bid price as follows:-

(a)        making any correction for errors

(b)       excluding  Provisional  Sums  and  the  provision,  if  any,  for  contingencies  in  the

Summary Bill of Quantities, but including competitively priced Day work, etc.

(c)        making an appropriate adjustment for any other acceptable variation or deviation.

3.         The estimated effect of the price adjustment provisions of the Conditions of Contract, applied over the period of execution of the Contract, shall not be taken into account in bid evaluation.

4.         If the bid of the successful bidder is seriously unbalanced in relation to the Employer’s estimate of the cost of work to be performed under the Contract, the Employer may require the bidder to produce detailed price analysis for any or all items of the Bill of Quantities to demonstrate  the internal consistency of those prices with the construction methods and schedule proposed. After evaluation of the price analysis, the Employer may require that the amount of the Performance Security set forth is sufficient to protect the Employer against financial loss in the event of default of the successful bidder under the Contract.

5.         General Performance of the Bidders

The Employer reserves the right to obtain information regarding performance of the bidders on their previously awarded contracts/works. The Employer may in case of consistent poor performance  of  the  bidder  as  reported  by  the  employers  of  the  previously  awarded contracts, interalia, refer the case to the Pakistan Engineering Council. Upon such reference, PEC may take such action as may be deemed appropriate under the circumstances of the case including black listing of such Bidder and debarring him from participation in the future bidding for similar works.

EVALUATION CRITERIA EXAMPLE FOR E&M WORKS

Preliminary Examination & Determination of Responsiveness of Bids

1.         Prior to determination of responsiveness,

(a)        The Engineer will examine the Bids to determine whether;

APPENDIX-B

i)          the Bid is complete and does not deviate from the scope, ii)         any computational errors have been made,

iii)        required sureties have been furnished,

iv)        the documents have been properly signed, v)         the Bid is valid till required period,

vi)        the Bid prices are firm during currency of contract if it is a fixed price bid, vii)       completion period offered is within specified limits,

viii)       the  Bidder/Manufacturer  is  eligible  to  bid  and  possesses  the  requisite experience,

ix)        the Bid does not deviate from basic technical requirements, and x)         the Bids are generally in order

b)         A bid is likely not to be considered, if;

i)          it is submitted by a Bidder who has participated in more than one Bid, ii)         it is received after the time and date fixed for its receipt,

iii)        it is submitted though fax, telex, telegram or email, iv)        it is not accompanied with Bid Security,

v)         it is unsigned,

vi)        its validity is less than specified,

vii)       it is submitted for incomplete scope of work,

viii)       it indicates completion period later than specified,

ix)        it indicates that prices quoted are not firm during currency of the contract,

x)         it indicates that Goods and material to be supplied do not meet eligibility requirements,

xi)        it indicates that Bid prices do not include the amount of income tax, xii)       if Bidder refuses to accept arithmetic corrections,

xiii)       it is materially and substantially different from the Conditions/Specifications of the Bidding Documents,

2.         Arithmetical errors will be rectified on the following basis:

If there is a discrepancy between the unit price and total price that is obtained by multiplying the unit price and quantity, the unit price shall prevail and the total price shall be corrected. If there is a discrepancy between the words and figures, the amount in words shall prevail. If there is a discrepancy between the total Bid Price entred in the Form of Bid and the total

shown in Schedule of Prices Summary, the amount stated in the Form of Bid will be corrected by the Employer/Engineer in accordance with the Corrected Schedule of Prices.

If the Bidder does not accept the corrected amount, his Bid will be rejected and his Bid

Security be forfeited.

3.         Prior to the detailed evaluation, the Engineer will determine the substantial responsiveness of each  Bid  to  the  Bidding  Documents.  For  purpose  of  these  Clauses,  a  substantially responsive  Bid  is  one  which  conforms  to  all  the  terms  and  conditions  of  the  Bidding Documents without material deviations.

A material deviation or reservation is one

(i)         which affect in any substantial way the scope, quality or performance of the Works;

(ii)        which limits in any substantial way, inconsistent with the Bidding Documents, the

Employer’s rights or the Bidder’s obligations under the Contract; or

(iii)       whose rectification would affect unfairly the competitive position of other bidders presenting substantially responsive bids.

The Engineer’s determination of a Bid responsiveness will be based on the contents of the

Bid itself without recourse to extrinsic evidence.

4.         A Bid determined as substantially non-responsive will be rejected and will not subsequently be made responsive by the Bidder by correction of the non-conformity.

5.         Any  minor  informality  or  non-conformity in a Bid which does not constitute a material deviation may be waived by Employer, provided such waiver does not prejudice to affect the relative ranking of any Bid.

6.         Conversion of Single Currency

6.1       To facilitate evaluation and comparison, the Employer/Engineer will convert, all Bid Prices expressed in the amount in various currencies in which Bid Price is payable, to Pak Rupees at the Telegraphic Transfer and Over Draft. (TT&OD) composite exchange rates selling published by State Bank of Pakistan and applicable to similar transactions, on the date of the opening of Bid.

7.         Detailed Evaluation of Bid

7.1       The Employer/Engineer will evaluate and compare only the bid previously determined to be substantially responsive as per requirements given hereunder:

7.2       Evaluation and Comparison of Bids

(a)        Bids will be evaluated for each item for complete scope of work

(b)       Basis of Price Comparison

The prices will be compared on the basis of the Evaluated Bid Price pursuant to

Para (e)(iii) herein below:

(c)        Technical Evaluation

It will be examined in detail whether the Works offered by the bidder complies with the Technical Provisions of the Bidding Documents. For this purpose, the bidder’s data submitted with the bid will be compared with technical information submitted with the bid regarding the Scope of Work will also be reviewed.

(d)       Commercial Evaluation

It   will   be   examined   in   detail   whether   the   bidders   comply   with   the commercial/contractual conditions of the Bidding Documents. It is expected that no major deviation/stipulation shall be taken by the bidders.

(e)        Evaluated Bid Price

In evaluating the bids, the Employer will determine for each bid in addition to the Bid Price, the following factors (adjustments) in the manner and to the extent indicated below to determine the Evaluated Bid Price.

(i)         Price Adjustment for Completeness in Scope of Work

In case of omission in the scope of work of a quoted item price adjustment for  the  omitted  item(s)  shall  be  applied  provided  that  the  Bidder  has mentioned in his bid that the same is covered in any other item(s).

The  price  adjustment  shall  not  justify  any  additional  payment  by  the Employer. The price(s) of omitted itme(s) shall be deemed covered by other prices in  Schedule of Prices

(ii)        Price Adjustment for Technical Compliance

The  cost  of  making  good  any  deficiency  resulting  from  technical  non compliance will be added to the corrected total Bid Price for comparison purposes only. The adjustments will be applied taking the average price quoted by other Bidders being evaluated in detail in their original Bids for corresponding item. In case of non availability of price from other Bidders, the price will be estimated by the Engineer/Employer.

(iii)       Price Adjustment for Commercial Compliance

The cost of making good any deficiency resulting from any quantifiable variations  and  deviations  from  the  Bid  Schedules  and  Conditions  of Contract, as determined by the Engineer/Employer will be added to the corrected total Bid Price for comparison purpose only. Adjustment for commercial compliance will be based on corrected total Bid Price.

(iv)       Price Adjustment for Deviation in Terms of Payment

If deviations are taken from the terms of payment/payment conditions as specified  in  the Bidding Documents and if such deviation is considered acceptable  to  the  Employer,  mark-up earned for any earlier payments involved in the terms outlined in the Bid as compared to those stipulated in the Conditions of Contract shall be calculated at the following mark-up rates.

-           for foreign currency component:            ___________ per annum

(insert rate)

-           for local currency component:               ___________ per annum

(insert rate)

and shall be added to the corrected total Bid Price for comparison purposes only.

(v)        Price adjustment for completion Schedule

Bids indicating completion in advance of the dates stated in Preamble to

Conditions of Contract, no credit will be given in this evaluation.

Bids indicating completion period later than the period set out in Preamble to Conditions of Contract shall be adjusted in the evaluation by adding a factor of 0.05% of the corrected total Bid Price for each calendar day of completion later than specified period of the completion.

Bids indicating completion beyond __________________ days later

(insert no of days)

than the dates set out in Preamble to Conditions of Contract, shall not be considered and rejected as non responsive.

9.         If the Bid of the successful bidder is seriously unbalanced in relation to the Employer’s estimate of the cost of work to be performed under the Contract, the Employer may require the bidder to produce detailed price analysis for any or all items of the Schedule of Prices to demonstrate the internal consistency of those prices with the construction methods and schedule proposed. After evaluation of the price analysis, the Employer may require that the

amount of the Performance Security be increased at the expense of the successful bidder to a level sufficient to protect the Employer against financial loss in the event of default of the successful bidder under the Contract.

10.       Domestic Preference

10.1     In the comparison of evaluated bidder, the Goods manufactured in Pakistan, will be granted a margin of preference in accordance with the following procedures, provided the bidder

(Classified in Group A) shall have established to the satisfaction of Employer that the manufacturing cost of such Goods includes a domestic value addition equal to at least 20% of the ex-factory Bid price of such Goods. Bidders applying for domestic preference shall substantiate their claim.

10.2     The Engineer will first review the bids to confirm the appropriateness of and to modify as necessary,  the  Bidders  group  classification  to  which  Bidders  assigned  their  Bids.  An incorrect classification of Group will not result in rejection of Bid but merely in the re- classification of the Bid into its appropriate Bid Group by the Engineer.

10.3     The comparison shall be Ex-factory price of the Goods to be offered from within Pakistan

(such prices to include all costs as well as custom duties and taxes paid or payable on raw materials and components or to be incorporated in the Goods) and the CIF Karachi price of the Goods to be offered from outside Pakistan.

10.4     The lowest evaluated Bid of each Group shall first be determined by comparing all evaluated renders in each Group among themselves without taking into account:

a)         In the case of Goods manufactured in Pakistan or Goods of foreign origin already located in Pakistan, sales tax, local body charges and other similar taxes which will be payable on the furnished Goods in Pakistan.

b)         In the case of Goods of foreign origin offered from abroad, customs duties and the import taxes which will be payable in furnished Goods in Pakistan.

10.5     The price preference to Group A bid will be:

i)          20%  of  the  ex-factory  bid  price,  if  the  value  addition  through  indigenous manufacturing is over 20% upto 30%.

ii)         25%  of  the  ex-factory  bid  price,  if  the  value  addition  through  indigenous manufacturing is over 30%.

10.6     The applicable price preference i.e. 20% or 25% as the case may be applied to Group A Bids by reducing 20% or 25% of the ex-factory bid price.

Dir/draft5/guidelines for procurement of Works

# Text boxes

Annex-II

IDENTIFICATION

Table -1

1.1        Name of Project                                  __________________________________

1.2        Employer

(a)  Name

___________________________________

(b)  Address

___________________________________

1.3        Contract number (identification)                 ___________________________________

1.4        Contract description                            ___________________________________

1.5        Engineer’s cost estimate(s)                  ___________________________________

1.6        Method of procurement (check one)     ICB_______LCB(NCB)_____ Other_____

1.7        Fixed price contract                                   Yes___________ No __________

Annex-II

BIDDING PROCESS

Table -2

2.1        Prequalification, carried out

(a)       Number of firms prequalified      __________________________________

2.2        Procurement Notice

(a)      Name of national newspaper

___________________________________

(b)      Issue date

___________________________________

c)       Number of individual firms notified

___________________________________

2.3        Standard Bidding Document

a)       Title, publication date

___________________________________

b)       Date of issue to bidders

___________________________________

2.4        Number of firms to whom documents

issued                                                          ___________________________________

2.5        Amendments to documents, if any

a)       List all ammendments No. &

dates

1.__________ 2. ________ 3.  _________

2.6        Date of pre-bid conference, if any             ___________________________________

2.7        Date minutes of the conference sent to bidders

___________________________________

Annex-II

BID SUBMISSION AND OPENING

Table -3

3.1        Bid submission deadline

(a)      Original date, time

___________________________________

b)       Extensions, if any

___________________________________

3.2        Bid opening date, time (Actual)           ___________________________________

3.3        Number of bids submitted                  ___________________________________

3.4        Bid validity period (days, weeks or months)

a)       Originally specified

b)       Extensions, if any

___________________________________

___________________________________

Annex-II

SUMMARY OF BID PRICES (AS READ OUT)

Table -4

Bidder Identification                                                             Read-out Bid Price(s)

Modifications or

Comments1

(e)

Bidder

(a)

Address

(b)

Amount

(c)

Currencies(s)

(if FE also demanded)

(d)

etc.

1.          Describe any modifications to the read-out bid, such as discounts offered, withdrawals, and alternative bids. Note also the absence of any required bid security or other critical items. Refer also para 3.1, Bid Opening.

Annex-II

RESULTS OF PRELIMINARY EXAMINATION

Table -5

Bidder

(a)

Verification

(b)

Eligibility

(c)

Bid Security

(d)

Completeness of Bid

(e)

Substantial

Responsiveness

(f)

Acceptance  for

Detailed Examination

(g)

etc.

Note:    For explanations of headings, see para-3.4. Additional columns may be needed, such as for responsiveness to technical conditions. See example in

Annex-III.

Annex-II

CORRECTIONS AND UNCONDITIONAL DISCOUNTS

Table -6

Bidder

Read-Out Bid Price(s)                           Corrections                      Corrected Bid

Price(s)

Unconditional

Discounts 2

Corrected/ Discounted Bid Price(s)

(a)

(f)=[(c)+(d)]-(e)

(i) = (f) - (h)

Amount (b)       Currency(ies)

(if FE also demanded)

(c)

Computational

Errors 1

(d)

Provisional

Sums

(e)

Percent

(g)

Amount

(h)

etc.

Note:    Only bids accepted as a result of preliminary examination (Table 5, column g) should be included in this and subsequent tables. Columns a, b and c in this table correspond to columns a, c and d respectively of table-4.

1.          Correction in column d may be positive or negative (negative should be shown in parenthesis).

2.          If the discount is offered as a percent, column h is normally the product of the amounts f and g . If the discount is provided as an amount, it is entered directly in column h.

Annex-II

ADDITIONS, ADJUSTMENTS AND PRICED DEVIATIONS

Table -7

Bidder

(a)

Corrected/Discounted

Bid Price

(b)

Additions 1

(c)

Adjustments1

(d)

Priced Deviations 1

(e)

Total Price

(f) = (b) + (c) + (d) + (e)

etc.

1.          Each insertion in columns c, d, or e should be footnoted and explained in adequate detail, accompanied by calculations. Refer to paras 3.5(d),

3.5(e) and 3.5(f) respectively.

Annex-II

PROPOSED CONTRACT AWARD

Table -8

1.   Lowest  evaluated  responsive  bidder

(proposed for contract award)

(a)      Name

___________________________________

b)       Address

___________________________________

2.   If bid from joint venture, list all

partners,  nationalities,  and

estimated shares of contract.

___________________________________

___________________________________

3.     Estimated    date    (month,    year)    of

contract signing.                                          ___________________________________

4.          Estimated completion period.

___________________________________

5.          Bid Price(s) (Read-out)1

Amount(s)

6.          Corrections for Errors 2

7.          Discounts 3

8.          Other Adjustments 4

9.          Proposed Award 5

1.          From Table 6, column b.

2.          From Table 6, column d.

3.          From Table 6, column h, including any cross-discounts.

4.          All adjustments should be explained in detail.

5.          Sum of the prices in Items 5 to 8

Annex-III

EXAMPLE OF PRELIMINARY EXAMINATION

Bidder

(a)

Verification

(b)

Eligibility

(c)

Bid Security

(d)

Completeness of

Bid

(e)

Substantial

Responsiveness

(f)

Acceptance for Detailed Examination

(g)

Bidder A                                 Yes                        Yes                             Yes                       Yes                             Yes                         Yes

Bidder B                                 No1                                     Yes                             Yes                        Yes                             Yes2                                       No

Bidder C                                 Yes                        Yes                             Yes                       Yes                             Yes                          Yes

Bidder D                                 Yes                        Yes                             No3                                      No                              Yes                          No

Bidder E                               Yes                           No                              No4                                     Yes                             Yes                          No

Bidder F                               Yes                          Yes                             Yes                        Yes                             Yes                         Yes

Bidder G                               Yes                          Yes                             Yes                        Yes                             Yes                         Yes

Bidder H                               Yes                          Yes                             Yes                        Yes                             Yes                          Yes

1.          Joint Venture agreement missing.

2.          Requires 25 percent mobilization advance; bid document states maximum of 15 percent. Deviation is minor or major depending on the resources of

Employer.

3.          Bid security not in required amount/format.

4.          Required validity period of security not met ( 8 weeks instead of 12 weeks ).