CONTENTS

|  | PART IIA - CONDITIONS OF PARTICULAR APPLICATION |  |
| --- | --- | --- |
|  |  | Page |
| 1.1 | Definitions | 159 |
| 2.1 | Engineer’s Duties and Authority | 159 |
| 2.2 | Engineer’s Representative | 160 |
| 2.7 | Engineer Not Liable | 160 |
| 5.1 | Language(s) and Law | 160 |
| 5.2 | Priority of Contract Documents | 161 |
| 6.6 | Shop Drawings | 161 |
| 6.7 | As-Built Drawings | 161 |
| 10.1 | Performance Security | 161 |
| 10.4 | Performance Security Binding on Variations and Changes | 161 |
| 14.1 | Programme to be Submitted | 162 |
| 14.3 | Cash Flow Estimate to be Submitted | 162 |
| 14.5 | Detailed Programme and Monthly Progress Report | 162 |
| 15.2 | Language Ability of Contractor’s Representative | 162 |
| 15.3 | Contractor’s Representative | 163 |
| 16.3 | Language Ability of Superintending Staff of Contractor | 163 |
| 16.4 | Employment of Local Personnel | 163 |
| 19.3 | Safety Precautions | 163 |
| 19.4 | Lighting Works at Night | 163 |
| 20.4 | Employer’s Risks | 164 |
| 21.4 | Exclusions | 164 |
| 25.5 | Insurance with National Insurance Corporation of Pakistan | 164 |
| 31.3 | Cooperation with Other Contractors | 165 |
| 34.2 | Rates of Wages and Conditions of Labour | 165 |
| 34.3 | Employment of Persons in the Service of Others | 165 |
| 34.4 | Housing for Labour | 165 |
| 34.5 | Health and Safety | 165 |
| 34.6 | Epidemics | 166 |
| 34.7 | Supply of Water | 166 |
| 34.8 | Alcoholic Liquor or Drugs | 166 |
| 34.9 | Arms and Ammunition | 166 |
| 34.10 | Festivals and Religious Customs | 166 |
| 34.11 | Disorderly Conduct | 166 |
| 34.12 | Compliance by Subcontractors | 166 |
| 35.2 | Records of Safety and Health | 167 |
| 35.3 | Reporting of Accidents | 167 |
| 36.6 | Use of Pakistani Materials and Services | 167 |
| 41.1 | Commencement of Works | 167 |
| 47.1 | Liquidated Damages for Delay | 167 |
| 47.3 | Bonus for Early Completion of Works | 167 |
| 48.2 | Taking Over of Sections or Parts | 168 |
| 51.2 | Instructions for Variations | 168 |
|  |  | Page No. |
| 52.1 | Valuation of Variations | 168 |
| 53.4 | Failure to Comply | 168 |
| 54.5 | Conditions of Hire of Contractor’s Equipment | 168 |
| 59.4 | Payments to Nominated Sub-contractors | 168 |
| 60.1 | Monthly Statements | 168 |
| 60.2 | Monthly Payments | 168 |
| 60.10 | Time for Payment | 169 |
| 60.11 | Secured Advance on Materials | 169 |
| 60.12 | Financial Assistance to Contractor | 170 |
| 63.1 | Blacklisting of Contractors | 171 |
| 65.2 | Special Risks | 171 |
| 67.3 | Arbitration | 171 |
| 68.1 | Notice to Contractor | 172 |
| 68.2 | Notice to Employer and Engineer | 172 |
| 70.1 | Increase or Decrease of Cost | 172 |
| 71.1 | Currency Restrictions | 174 |
| 73.1 | Payment of Income Tax | 174 |
| 74.1 | Bribery and Collusion | 174 |
| 75.1 | Termination of Contract for Employer’s Convenience | 175 |
| 76.1 | Liability of Contractor | 175 |
| 77.1 | Joint and Several Liability | 176 |
| 78.1 | Details to be Confidential | 176 |
|  | PART IIB – CONDITIONS OF PARTICULAR APPLICATION | 177 |
|  | SPECIFICATIONS- SPECIAL PROVISIONS | 180 |
|  | SPECIFICATIONS – TECHNICAL PROVISIONS | 181 |
|  | DRAWINGS | 182 |

PART 11 A - CONDITIONS OF PARTICULAR APPLICATION

(Mandatory Provisions not to be Amended / Substituted)

1.1	Definitions

(a) (i)	The Employer is ........................................................ ... ....... ...... ........................................................(insert name along with his full address).

(a) (iv)	The Engineer is ................................................................................

.........................................................................................................(insert name of the Firm/Company/Person nominated as Engineer alongwith his full address), or any other competent person appointed by the Employer, and notified to the Contractor, to act in replacement of the Engineer. Provided always that except in cases of professional misconduct, the outgoing Engineer to formulate his certifications/recommendations in relation to all outstanding matters, disputes and claims relating to the execution of the Works during his tenure.

Add the following paragraph:

(a)(vi)	“ Bidder or Tenderer” means any person or persons, company, corporation, firm or joint venture submitting a Tender.

(b)(v)	Add the following at the end of the paragraph:

The word “Tender” is synonymous with “Bid” and the word “Tender Documents” with “Bidding Documents”.

Add the following paragraph:

(b)(ix)	“Programme” means the programme to be submitted by the Contractor in accordance with Sub-Clause 14.1 and any approved revisions thereto.

(e)(i)	Delete the text and substitute:

“Contract Price” means the sum stated in the Letter of Acceptance as payable to the Contractor for the execution and completion of the Works subject to such additions thereto or deductions therefrom as may be made and remedying of any  defects therein in accordance with the provisions of the Contract.

2.1	Engineer's Duties and Authority

(b)	Delete the text and substitute:

The Engineer shall obtain the specific approval of the Employer before carrying out his duties in accordance with the clauses specified in Part-IIB.

If in the opinion of the Engineer an emergency occurs affecting the safety of life or of the Works or of adjoining property, the Engineer may, without  recourse to the provisions as set out in the above paragraph, and without relieving the Contractor of any of his duties and responsibilities under the Contract, instruct the Contractor to execute all such work or to do all such things as may, in the opinion of the Engineer, be necessary to abate or reduce the risk.  The Contractor shall forthwith comply with any such instruction of the Engineer.  The Engineer shall determine an addition to the Contract Price, in respect of such instruction, in accordance with Clause- 52 and shall notify the Contractor accordingly, with  a copy to the Employer.

2.2	Engineer’s Representative

Add the following paragraph:

The Employer shall ensure that the Engineer’s Representative is a professional engineer as defined in the Pakistan Engineering Council Act 1975 (V of 1976)

Add the following Sub-Clause:

2.7	Engineer not Liable

Approval, reviews and inspection by the Engineer of any part of the Works does not relieve the Contractor from his sole responsibility and liability for the supply of materials, plant and equipment for construction of the Works and their parts in accordance with the Contract and neither the Engineer's authority to act nor any decision made by him in good faith as provided for under the Contract whether to exercise or not to exercise such authority shall give rise to any duty or responsibility of the Engineer to the Contractor, any Subcontractor, any of their representatives or employees or any other  person performing any portion of the Works.

5.1	Language(s) and Law

(a)	The Contract Documents , shall be drawn up in the English language.

(b)	The Contract shall be subject to the Laws of Islamic Republic of  Pakistan.

# 5.2	Priority of Contract Documents

Delete the documents listed at (1) to (6) of the Sub-Clause and substitute:

(1)	The Contract Agreement (if completed);

(2)	The letter of Acceptance;

(3)	The Tender;

(4)	The Conditions of Particular Application – Part IIB;

(5)	The Conditions of Particular Application – Part IIA;

(6)	The General Conditions – Part I;

(7)	The Drawings;

(8)	The Specifications;

(9)	The priced Bill of Quantities;

(10)	________________________________________________;

(11)	________________________________________________;

(12)	________________________________________________;

In case of discrepancies between drawings, those of larger scale shall govern unless they are superseded by a drawing of later date regardless of scale. All Drawings and Specifications shall be interpreted in conformity with the Contract and these Conditions. Addendum, if any, shall be deemed to have been incorporated at the appropriate places in the documents forming the Contract.

Add the following Sub-Clauses:

6.6		Shop Drawings

The Contractor shall submit to the Engineer for review 3 copies of all shop and erection drawings applicable to this Contract as per provision of relevant Sub-Clause of the Contract.

Review and approval by the Engineer shall not be construed as a complete check but will indicate only that the general method of construction and detailing is satisfactory and that the Engineer’s review or approval shall not relieve the Contractor of any of his responsibilities under the Contract.

6.7	As-Built Drawings

At the completion of the Works under the Contract, the Contractor shall furnish to the Engineer 6 copies and one  reproducible of all drawings amended to comply with the Works as built. The price  of such Drawings shall be deemed to be included in the Contract Price.

10.1	Performance Security

Delete the text and substitute:

The Contractor shall provide Performance Security to the Employer in the prescribed form. The said Security shall be furnished or caused to be furnished by the Contractor within 28 days after the receipt of the Letter of Acceptance. The Performance Security shall be of an amount not less than 10% of the Contract Price stated in the Letter of Acceptance. Such Security shall be in the form of either (a) bank guarantee from any Scheduled Bank of Pakistan or (b) bank guarantee from a bank located outside Pakistan duly counter-guaranteed by a Scheduled Bank of Pakistan or (c) Bond from an insurance company acceptable to the Employer.

The cost of complying with requirements of this Sub-Clause shall be borne by the Contractor.

Add the following Sub-Clause:

10.4	Performance Security Binding on Variations and Changes

The Performance Security shall be binding irrespective of changes in the quantities or variations in the Works or extensions in Time for Completion of the Works which are granted or agreed upon under the provisions of the Contract.

14.1	Programme to be Submitted

The programme shall be submitted within 42 days from the date of receipt of Letter of Acceptance, in such form as specified in Part II-B

14.3	Cash Flow Estimate to be Submitted

The detailed Cash Flow Estimate shall be submitted within 21 days from the date of receipt of Letter of Acceptance

Add the following Sub-Clause:

14.5	Detailed Programme and Monthly Progress Report

a)	For purposes of Sub-Clause 14.1, the Contractor shall submit to the Engineer detailed programme for the following:

(1)	Execution of Works;

(2)	Labour Employment;

(3)	Local Material Procurement;

(4)	Material Imports, if any; and

(5)	Other details as required by the Engineer.

(b)	During the period of the Contract, the Contractor shall submit to the Engineer not later than the 8th day of the following month, 10 copies each of Monthly Progress Reports covering:

(1)	A Construction Schedule indicating the monthly progress in percentage;

(2)	Description of all work carried out since the last report;

(3)	Description of the work planned for the next 56 days sufficiently detailed to enable the Engineer to determine his programme of inspection and testing;

(4)	Monthly summary of daily job record;

(5)	Photographs to illustrate progress ;and

(6)	Information about problems and difficulties encountered, if any, and proposals to overcome the same.

(c)	During the period of the Contract, the Contractor shall keep a daily record of the work progress, which shall be made available to the Engineer as and when requested. The daily record shall include particulars of weather conditions, number of men working, deliveries of materials, quantity, location and assignment of Contractor’s equipment.

Add the following Sub-Clauses:

15.2	Language Ability of Contractor’s Representative

The Contractor’s authorised representative shall be fluent in the English language.

15.3	Contractor’s Representative

The Contractor’s authorised representative and his other professional engineers working at site shall register themselves with the Pakistan Engineering Council.

The Contractor’s authorised representative at Site shall be authorised to exercise adequate administrative  and financial powers on behalf of the Contractor so as to achieve completion of the Works as per the Contract.

Add the following Sub-Clauses:

16.3	Language Ability of Superintending Staff of Contractor

A reasonable proportion of the Contractor's superintending staff shall have a working knowledge of the English language.

16.4	Employment of Local Personnel

The Contractor is encouraged, to the extent practicable and reasonable, to employ staff and labour from sources within Pakistan.

Add the following Sub-Clauses:

19.3	Safety Precautions

In order to provide for the safety, health and welfare of' persons, and for prevention of damage of any kind, all operations for the purposes of or  in connection with the Contract shall be carried out in compliance with the Safety Requirements of the Government of Pakistan with such modifications thereto as the Engineer may authorise or direct and the Contractor shall take or cause to be taken much further measures and comply with such  further requirements as  the Engineer may determine to be reasonably necessary for such purpose.

The Contractor shall make, maintain and submit reports to the Engineer concerning safety, health and welfare of persons and damage to property, as the Engineer may from time to time prescribe.

19.4	Lighting Work at Night

In the event of work being carried out at night, the Contractor shall at his own cost, provide and maintain such good and sufficient light as will enable the work to proceed satisfactorily and without danger. The approaches to the Site and the Works where the night-work is being carried out shall be sufficiently lighted. All arrangement adopted for such lighting shall be to the satisfaction of the Engineer’s Representative.

20.4	Employer’s Risks

The Employer’s risks are:

Delete the text and substitute:

(a)	insofar as they directly affect the execution of the Works in Pakistan:

(i)	war and hostilities (whether war be declared or not), invasion, act of foreign enemies,

(ii)	rebellion, revolution, insurrection, or military or usurped power, or civil war,

(iii)	ionizing radiations, or contamination by radioactivity from any nuclear fuel, or from any nuclear waste from the combustion of nuclear fuel, radioactive toxic explosive or other hazardous properties of any explosive nuclear assembly or nuclear component thereof,

(iv)	pressure waves caused by aircraft or other aerial devices travelling at sonic or supersonic speeds,

(v)	riot , commotion or disorder, unless solely restricted to the employees of the Contractor or of his Subcontractors and arising from the conduct of the Works;

(b)	loss or damage due to the use or occupation by the Employer of any Section or part of the Permanent Works, except as may be provided for in  the Contract.

(c)	loss or damage to the extent that it is due to the design of the Works, other than any part of the design provided by the Contractor or for which the Contractor is responsible; and

(d)	any operation of the forces of nature (insofar as it occurs on the Site) which an experienced contractor:-

(i)	could not have reasonably foreseen, or

(ii)	could  reasonably have foreseen, but against which he could not reasonably have taken at least one of the following measures:-

(a)	prevent loss or damage to physical property from occurring by taking appropriate measures, or

(b)	insure against.

21.4	Exclusions

Delete the text and substitute:

There shall be no obligation for the insurances in Sub-Clause 21.1 to include loss or damage caused by the risks listed under Sub-Clause 20.4 paras (a) (i) to (iv).

Add the following Sub-Clause:

25.5	Insurance with National Insurance Corporation of Pakistan

The Contractor shall be obliged to place all insurances relating to the Contract (including, but not limited to, the insurances referred to in Clauses 21, 23 and 24) with National Insurance Corporation of Pakistan.Add the following Sub-Clause:

31.3	Co-operation with other Contractors

During the execution of the Works, the Contractor shall co-operate fully with other contractors working  for the Employer at and in the vicinity of the Site and also shall provide adequate precautionary facilities not to make himself a nuisance to local residents and other contractors.

Add the following Sub-Clauses:

34.2	Rates of Wages and Conditions of Labour

The Contractor shall pay rates of' wages and observe conditions of  labour not less favourable than those established for the trade or industry where the work is carried out.  In the absence of any rates of wages or conditions of labour so established, the Contractor shall pay rates of wages and observe conditions of labour which are not less favourable than the general level of  wages and conditions observed by other employers whose general circumstances in the trade or in industry in which the Contractor is engaged are similar.

34.3	Employment of Persons in the Service of Others

The Contractor shall not recruit his staff and labour from amongst the persons in the services of the Employer or the Engineer; except with the prior written consent of the Employer or the Engineer, as the case may be.

34.4	Housing for Labour

Save insofar as the Contract otherwise provides, the Contractor shall provide and maintain such housing accommodation and amenities as he may consider necessary for all his supervisory staff and labour, employed for the purposes of or in connection with the Contract including all fencing, electricity supply, sanitation, cookhouses, fire prevention, water supply and other requirements in connection with such housing accommodation or amenities.  On completion of the Contract, unless otherwise agreed with the Employer, the temporary camps or housing provided by the Contractor shall be removed and the Site reinstated to its original condition, all to the approval of the Engineer.

34.5	Health and Safety

Due precautions shall be taken by the Contractor, and at his own cost, to ensure the safety of his staff and labour at all times throughout the period of the Contract.  The Contractor shall further ensure that suitable arrangements are made for the prevention of epidemics and for all necessary welfare and hygiene requirements.

34.6	Epidemics

In the event of any outbreak of illness of an epidemic nature, the Contractor shall comply with and carry out such regulations, orders and requirements as may be made by the Government, or the local medical or sanitary authorities, for purpose of dealing with and overcoming the same.

34.7	Supply of Water

The Contractor shall, so far as is reasonably practicable, having regard to local conditions, provide on the Site, to the satisfaction of the Engineer or his representative, adequate supply of drinking and other water for the use of his staff and labour.

34.8	Alcoholic Liquor or Drugs

The Contractor shall not, otherwise than in accordance with the Statutes, Ordinances and Government Regulations or Orders for the time being in force, import, sell, give, barter or otherwise dispose of any alcoholic liquor or drugs, or permit or suffer any such importation, sale, gift, barter or disposal by his Subcontractors, agents, staff or labour.

34.9	Arms and Ammunition

The Contractor shall not give, or otherwise dispose of to any person or persons, any arms or ammunition of any kind or permit or suffer the same as aforesaid.

34.10	Festivals and Religious Customs

The Contractor shall in all dealings with his staff and labour have due regard to all recognised festivals, days of rest and religious and other customs.

34.11	Disorderly Conduct

The Contractor shall at all times take all reasonable precautions to prevent any unlawful, riotous or disorderly conduct by or amongst staff and labour and for the preservation of peace and protection of persons and property in the neighbourhood of the Works against the same.

34.12	Compliance by Subcontractors

The Contractor shall be responsible for compliance by his Subcontractors of the provisions of this Clause.

Add the following Sub-Clauses:-

35.2	Records of Safety and Health

The Contractor shall maintain such records and  make such reports concerning safety, health and welfare of persons and damage to property as the Engineer may from time to time prescribe.

35.3	Reporting of Accidents

The Contractor shall report to the Engineer details of any accident as soon as possible after its occurrence. In the case of any fatality or serious accident, the Contractor shall, in addition, notify the Engineer immediately by the quickest available means.

Add the following Sub-Clause:-

36.6	Use of Pakistani Materials and Services

The Contractor shall , so far as may be consistent with the Contract, make the maximum use of materials, supplies, plant and equipment indigenous to or produced or fabricated in Pakistan and services, available in Pakistan provided such materials, supplies, plant, equipment and services shall be of required standard.

41.1	Commencement of Works

Delete the text and substitute:

The Contractor shall commence the Works on Site within the period named in Appendix to Tender from the date or receipt by him from the Engineer of a written Notice to Commence. Thereafter, the Contractor shall proceed with the Works with due expedition and without delay.

47.1	Liquidated Damages for Delay

In the fifth line of the Sub-Clause, delete the words “ and not as a penalty”

Add the following paragraphs at the end of the Sub-Clause:-

The liquidated damages for each day of delay in completion of the whole of the Works, or if applicable any Section, shall be as given in Appendix to Tender, subject to a maximum of 10% of the Contract Price stated in the Letter of Acceptance.

Add the following Sub-Clause :-

47.3	Bonus for Early Completion of Works

The Contractor shall in case of earlier completion for either whole or part(s) of the Works pursuant to Clause 48.1 and 48.2(a) respectively of the General Conditions of Contract, be paid bonus up-to a limit and at a rate equivalent to 50% of the relevant limit and rate of liquidated damages prescribed under Clause 47.1 above.

48.2	Taking Over of Sections or Parts

For the purposes of para (a) of this Sub-Clause, separate Times for Completion shall be as indicated in Part IIB.

51.2	Instructions for Variations

At the end of the first sentence, after the word  “Engineer", add the words “in writing”.

52.1	Valuation of Variations

In the tenth line, after the words “ Engineer shall” add the following:-

Within a period not exceeding one-eighth of the completion time subject to a minimum of 56 days from the date of disagreement whichever is later.

53.4	Failure to Comply

Delete this Sub-Clause in its entirety

54.5	Conditions of Hire of Contractor’s Equipment

Add the following paragraph

The Contractor shall, upon request by the Engineer at any time in relation to any item of hired Contractor’s Equipment, forthwith notify the Engineer in writing the name and address of the Owner of the equipment and shall certify that the agreement for the hire thereof contains a provision in accordance with the requirements set forth above.

59.4	Payments to Nominated Sub-Contractors

For the purposes of this Sub-Clause, provisions made by the Employer in Part II-B shall apply.

60.1	Monthly Statements

In the first line after the word “shall”, add the following:

“on the basis of the joint measurement of work done under Clause 56.1,”

In Para  (c) delete the words “the Appendix to Tender” and substitute “ Sub-Cause 60.11 (a)(6) hereof”.

60.2	Monthly Payments

In the first line, substitute “28” by “14”.

60.10	Time for Payment

Delete the text and substitute:

The amount due to the Contractor under any Interim Payment Certificate issued by the Engineer pursuant to this Clause, or to any other terms of the Contract, shall , subject  to Clause 47, be paid by the Employer  to the Contractor within 14 days in the case of local currency and within 42 days in the case of foreign currency, after such Interim Payment Certificate has been delivered to the Employer, or, in the case of the Final Certificate referred to in Sub Clause 60.8, within 28 days in the case of local and within 56 days in case of foreign currency, after such Final Payment Certificate has been delivered to the Employer. In the event of the failure of the Employer to make payment within the times stated, the Employer shall pay to the Contractor compensation at the rate of 8% per annum, upon all sums unpaid from the date by which the same should have been paid. The provisions of this Sub-Clause are without prejudice to the Contractor’s entitlement under Clause 69.

Add the following Sub-Clauses:

60.11	Secured Advance on Materials

a)	The Contractor shall be entitled to receive  from the Employer Secured Advance against an indemnity bond acceptable to the Employer of such sum as the Engineer may consider proper in respect of non-perishable materials brought  at the Site but not yet incorporated in the Permanent Works provided that:

(1)	the materials are in accordance with the Specifications for the Permanent Works;

(2)	Such materials have been delivered to the Site and are properly stored and protected against loss or damage or deterioration to the satisfaction of the Engineer but at the risk and cost of the Contractor;

(3)	The Contractor’s records of the requirements, orders, receipts and use of materials are kept in a form approved by the Engineer , and such records shall be available for inspection by the Engineer;

(4)	The Contractor shall submit with his monthly statement the estimated value of the materials on Site together with such documents as may be required by the Engineer for the purpose of valuation of materials and providing evidence of ownership and payment therefor;

(5)	Ownership of such materials shall be deemed to vest in the Employer and these materials shall not be removed from the Site or otherwise disposed of without written permission of the Employer; and

(6)	The sum payable for such materials on Site shall not exceed 75 % of the (i) landed cost of imported materials, or (ii) ex-factory / ex-warehouse price of locally manufactured or produced materials , or (iii) market price of other materials.

(b)	The recovery of Secured Advance paid to the Contractor under the above provisions shall be effected from the monthly payments on actual consumption basis.

60.12	Financial Assistance to Contractor

Financial assistance shall be made available to the Contractor by the Employer by adopting any one of the following three Alternatives, as stated in Part-II B.

Alternative One: Mobilization Advance

a)	An interest-free Mobilization Advance up to 15 % of the Contract Price stated in the Letter  of Acceptance shall be paid by the Employer to the Contractor in two equal parts upon submission by the Contractor of a Mobilization Advance Guarantee for the full amount of the Advance in the specified form from a Scheduled Bank of Pakistan or an insurance company acceptable to the Employer:

(1)	First part within 14 days after signing of the Agreement or date of receipt of Engineer’s Notice to Commence, whichever is earlier; and

(2)	Second part within 42 days from the date of payment of the first part, subject to the satisfaction of the Engineer as to the state of mobilization of the Contractor.

b)	This Advance shall be recovered in instalments; first instalment at the expiry of third month after the date of payment of first part of Advance and the last instalment two months before the date of completion of the Works as per Clause 43 hereof.

The schedule of recovery of the Mobilization Advance shall be as given in Part-II B.

Alternative Two: Mobilization/ Demobilization Cost

Mobilization Cost shall be paid to the Contractor as a part of the priced Bill of Quantities. This cost shall not exceed 10 % of the Tender Price and shall be paid to the Contractor as follows:

(i)	80 % of the Mobilization Cost shall be paid for mobilization at Site. This payment shall  be in three stages as follows:

Stage I:	20 % of mobilization cost upon obtaining and furnishing of Performance Security and insurance policies and construction of camp and housing facilities as required under the Contract;

Stage II:	30 % of mobilization cost upon providing & installing preliminary requirements of Contractor’s equipment, materials and temporary structures for the commencement of Works to the satisfaction of the Engineer and achieving 3 % value of the Works (excluding payment under Stage-I);

Stage III:	30 % of mobilization cost upon providing balance Contractor’s Equipment to complete full requirement for the entire work and after achievement of progress to the extent of 6 % value of the Works (excluding payments under Stages I and II); and

(ii)	20 % of Mobilization Cost shall be paid for operation and maintenance of the constructed facilities and for demobilization as per schedule of payment to be submitted by the Contractor in accordance with Clause 57.2 and approved by the Engineer.

Alternative Three: Materials Supplied by Employer

The Employer shall supply to  the Contractor materials, like cement, steel, bitumen or any other material whichever deemed necessary to complete the project; and the cost thereof shall be recovered from the Contractor through monthly statements on the basis of actual consumption.

The list of materials, quantities and rates to be charged to the Contractor shall be as given in Part II-B

63.1	Black Listing of Contractors

Add the following para at the end of the Sub-Clause:

Provided further that in addition to the action taken by the Employer against the Contractor under this Clause, the Employer may also refer the case of default of the Contractor to Pakistan Engineering Council for punitive action under the Construction and Operation of Engineering Works Bye-Laws 1987, as amended from time to time.

65.2	Special Risks

Delete the text and substitute:

The Special Risks are the risks defined under Sub-Clause 20.4 paras a (i) to (v).

67. 3	Arbitration

In the sixth to eight lines, delete the words “ shall be finally settled .......... appointed under such Rules” and substitute the following:

shall be finally settled under the provisions of the Arbitration Act, 1940 as amended or any statutory modification or re-enactment thereof for the time being in force.

Add the following paragraph:

The place of arbitration is stated in Part-II B.

68.1	Notice to Contractor

Add the following paragraph:

For the purposes of this Sub-Clause, the Contractor shall, immediately after receipt of Letter of Acceptance, intimate in writing to the Employer and the Engineer by registered post, the address of his principal place of business or any change in such address during the period of the Contract.

68.2	Notice to Employer and Engineer

For the purposes of this Sub-Clause, the respective address are:

a)	The Employer :

(to be filled in as appropriate)

b)	The Engineer:

(to be filled in as appropriate)

70.1	Increase or Decrease of Cost

Add the following paragraphs”

(a)	The Contractor is deemed to have quoted rates and prices given in the Contract on the basis of labour wages/ out-goings and prices of certain specified materials and equipment prevailing on the date 28 days prior to the date of opening of the Tender.  Applicable Basic Prices and method of calculating price adjustment is given in Appendix to Tender.

(b)	During the currency of the Contract the Contractor shall be paid compensation for additional payments / expenses to which he may be exposed on account of changes/additions in the rates or quantum of such wages/ out-goings and prices of materials brought about by any changes in the fiscal policies of any Federal/Provincial Government, Local Body and / or Government-controlled/owned  Corporation or Company,	applicable to the Contract.  Similarly, the  Contractor shall be liable to pay to the Employer any saving which he may make on such wages/out-goings and prices of materials because of any change in the aforesaid fiscal policies.

(c)	Adjustment shall be allowed only for the quantities of materials specified in Appendix to Tender (except High Speed Diesel) which have actually been incorporated in the Permanent Works during the corresponding period of increase or decrease.

(d)	Adjustment shall be allowed for the Specified Materials and Labour according to Notes (1) and Note (2) respectively in the Appendix to Tender

(e)	All claims for additional payments under this Clause shall be lodged by the Contractor with  the Engineer  within such reasonable time from the date of occurrence of the event which, according to the Contractor, entitles him to such  additional payments by the Employer but in no case after the expiry of 28 days thereof.  Such claims shall invariably be supported with all necessary/relevant/material details and  particulars required for proper verification thereof and the Engineer shall be entitled to require the Contractor to provide such further details/information as may be so required for due and effective verification of such claims.

(f)	The Engineer shall verify and certify for payment, if any, all claims lodged by the Contractor under this Clause within a period not exceeding 28 days from the date on which the same are submitted by the Contractor as aforesaid.

(g)		The Employer shall make payment against the certification of the Engineer made pursuant to para (f) above along with the monthly payment/any other payment falling due immediately after the date of such certification.

(h)		In case the Employer is entitled to recover from the Contractor any sum or sums under  this Clause arising from any decrease in the said wages / out-goings and prices for materials, the provisions of this Clause shall mutatis mutandis apply to such recoveries by the Employer.

(i)		If the Contractor fails to complete the Works within the Time for Completion prescribed under Clause 43, adjustment of prices thereafter until the date of completion of the Works shall be made using either the indices or prices relating to the prescribed time for completion, or the current indices or prices, whichever are more favourable to the Employer, provided that if extension of time is granted pursuant to Clause 44 the above provision shall apply only to adjustments made up to the expiry of such extension of time.

(j)		Provisions contained in this Sub-Clause shall be incorporated in the Sub-contract/s by the Contractor.

71.1	Currency Restrictions

Delete this Sub-Clause in its entirety:

Add the following Sub-Clause:

73.1	Payment of Income Tax

The Contractor,  Subcontractors and their employees shall be responsible for payment of all their income tax, super tax and other taxes on income arising out of the Contract and the rates and prices stated in the Contract shall be deemed to cover all such taxes.

Add the following Sub-Clause:

74.1	Bribery and Collusion

Fraud and Corruption

It is the policy of the PSML  to require its staff and its Vendor / consultants to observe the highest standard of ethics during the selection and execution of such contracts. In pursuance of this policy,  PSML :

(a) Defines, for the purposes of this provision, the terms set forth below:

(i) 	“Corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, of any thing of value to influence the action of a public official in the selection process or in contract execution; and

(ii)  	“Fraudulent practice” means a misrepresentation or omission of facts in order to influence a selection process or the execution of a contract;

(iii) 	“Collusive practices” means a scheme or arrangement between two or more consultants  with or without the knowledge of PSML , designed to establish prices at artificial, noncompetitive levels and to deprive  PSML  of the benefits of free and open competition;

(iv) 	“Coercive practices” means harming or threatening to harm, directly or indirectly, persons or their property to influence their participation in a procurement process, or affect the execution of a contract.

(b) will reject a proposal for award if it determines that the consultant recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices in competing for the contract in question;

(c) will sanction a contractor, including declaring the contractor ineligible, either indefinitely or for a stated period of time, to be awarded a PSML  contract if it at any time determines that the consultant has, directly or through an agent, engaged in corrupt, fraudulent, collusive or coercive practices.

(1)	The Employer shall be entitled to terminate the Contract and recover from the Contractor the amount of any loss resulting from such termination if the Contractor shall have offered or given to any person any gift or consideration of any kind as an inducement or reward for doing, or

`	forbearing to do, any action in relation to obtaining, or in the execution of the Contract or any other contract the Employer, or for showing favour to any person in relation to the Contract or any other contract with the Employer, or if any of the like acts shall have been done by any person employed by the Contractor or acting on his behalf  (whether with or without the knowledge of the Contractor), or if the Contractor shall have come to any agreement with another contractor or number of contractors whereby  an agreed quotation or estimate shall be offered as a bid to the Employer by one or more Contractors.

(2)		In the event of such termination, the Contractor shall:

(a)	proceed as provided in Sub-Clause 65.7 hereof; and

(b)	be paid by the Employer as provide in Sub-Clause 65.8 hereof, provided that  any loss referred to in Sub-Clause (1) of this Sub-Clause shall first be deducted

Add the following Sub-Clause:

75.1	Termination of Contract for Employer's Convenience

The Employer shall be entitled to terminate the Contract at any time for the Employer's convenience after giving 56 days prior notice to the Contractor, with a copy to the Engineer.  In the event of such termination, the Contractor :

(a)	shall proceed as provided in Sub-Clause 65.7 hereof; and

(b)	shall be paid by the Employer as provided in Sub-Clause 65.8 hereof.

Add the following Sub-Clause:

76.1	Liability of Contractor

The Contractor or his Subcontractors or assigns shall follow strictly, all relevant labour laws including the Workmen's Compensation Act and the Employer shall be fully indemnified for all claims, damages etc. arising out of any dispute between the Contractor, his Subcontractors or assigns and the labour employed by them.

Add the following Sub-Clause:.

77.1	Joint and Several Liability

If the Contractor is a joint venture of two or more persons, all such persons shall be jointly and severally bound to the Employer for the fulfilment of the terms of the Contract and shall designate one of such persons to act as leader with authority to bind the joint venture. The composition or the constitution of the joint venture shall not be altered without the prior consent of the Employer.

Add the following Sub-Clause:

78.1	Details to be Confidential

The Contractor shall treat the details of the Contract as private and confidential, save in so far as may be necessary for the purposes thereof, and shall not publish or disclose the same or any particulars thereof in any trade or technical paper or elsewhere without the prior consent in writing of the Employer or the Engineer. If any dispute arises as to the necessity of any publication or disclosure for the purpose of the Contract, the same shall be referred to the decision of the Engineer whose award shall be final.

Amendment-Public Procurement Rules 2004

Rule 46.  	Record of procurement proceedings.-  (1) 	All procuring agencies shall maintain a record of their respective procurement proceedings along with all associated documentation for a minimum period of five years.

(2)	 Such maintenance of record shall be subject to the regulations framed in this regard from time to time.

Rule 47.	Public access and transparency.-  As soon as a contract has been awarded the procuring agency shall make all documents related to the evaluation of the bid and award of contract public:

Provided that where the disclosure of any information related to the award of a contract is of proprietary nature or where the procuring agency is convinced that such disclosure shall be against the public interest, it can withhold only such information from public disclosure subject to the prior approval of the Authority.

## PART IIA -CONDITIONS OF PARTICULAR APPLICATION

| Index | Clause |  |
| --- | --- | --- |
| Alcoholic Liquor or Drugs | 34.8 |  |
| Arbitration | 67.3 |  |
| Arms and Ammunition | 34.9 |  |
| As-Built Drawings | 6.7 |  |
| Bribery and Collusion | 74.1 |  |
| Cash Flow Estimate to be Submitted | 14.3 |  |
| Commencement of Works | 41.1 |  |
| Compliance by Sub-Contractors | 34.12 |  |
| Conditions of Hire of Contractor’s Equipment | 54.5 |  |
| Contractors Representative | 15.3 |  |
| Co-operation with Other Contractors | 31.3 |  |
| Currency Restrictions | 71.1 |  |
| Definitions | 1.1 |  |
| Detailed Programme and Monthly Progress Report | 14.5 |  |
| Details to be Confidential | 78.1 |  |
| Disorderly conduct | 34.11 |  |
| Employer’s Risks | 20.4 |  |
| Employment of Local Personnel | 16.4 |  |
| Employment of Persons in the Service of Others | 34.3 |  |
| Engineer not Liable | 2.7 |  |
| Engineer’s Duties and Authority | 2.1 |  |
| Engineer’s Representative | 2.2 |  |
| Epidemics | 34.6 |  |
| Exclusions | 21.4 |  |
| Failure to Comply | 53.4 |  |
| Festivals and Religious Customs | 34.10 |  |
| Financial Assistance to Contractor | 60.12 |  |
| Health and Safety | 34.5 |  |
| Housing for Labour | 34.4 |  |
| Increase or Decrease of Cost | 70.1 |  |
| Instructions for Variations | 51.2 |  |
| Insurance with National Insurance Corporation of Pakistan | 25.5 |  |
| Joint and Several Liability | 77.1 |  |
| Language Ability of Contractor’s Representative | 15.2 |  |
| Language Ability of Superintending Staff of Contractor | 16.3 |  |
| Language and Law | 5.1 |  |
| Liability of Contractor | 76.1 |  |
| Lighting Work at Night | 19.4 |  |
| Liquidated Damages for Delay | 47.1 |  |
| Monthly Payments | 60.2 |  |
| Monthly Statements | 60.1 |  |
| Notice to Contractor | 68.1 |  |
| Notice to Employer and Engineer | 68.2 |  |
| Payment of Income Tax | 73.1 |  |
| Index | Clause |  |
| Payments of Nominated Sub-Contractors | 59.4 |  |
| Performance Security | 10.1 |  |
| Performance Security Binding on Variation and Changes | 10.4 |  |
| Priority of Contract Documents | 5.2 |  |
| Programme to be Submitted | 14.1 |  |
| Rates of Wages and Conditions of Labour | 34.2 |  |
| Records of Safety and Health | 35.2 |  |
| Reporting of Accidents | 35.3 |  |
| Safety Precautions | 19.3 |  |
| Secured Advance on Materials | 60.11 |  |
| Shop Drawings | 6.6 |  |
| Special Risks | 65.2 |  |
| Supply of Water | 34.7 |  |
| Taking Over of Sections or Parts | 48.2 |  |
| Termination of Contract for Employer’s Convenience | 75.1 |  |
| Time for Payment | 60.10 |  |
| Use of Pakistan Materials and Services | 36.6 |  |
| Valuation of Variations | 52.1 |  |

PART IIB

CONDITIONS OF PARTICULAR APPLICATION

SPECIFICATIONS-

SPECIAL PROVISIONS

SPECIFICATIONS –

TECHNICAL PROVISIONS

DRAWINGS